## Module Summary
Pulse CRM — Module-wise Test Execution & Gap Report
Executed live (web UI via Playwright + API as 8 roles) against pulse-crm.theclustox.com. Unimplemented features are reported as FAILED gaps. 2026-06-29
Module | Plan cases | Live checks PASS | Live FAIL | GAPS = FAIL (not implemented) | Built but not auto-tested | Module verdict
Leads | 64 | 30 | 0 | 1 | 33 | GAPS — features missing
Training | 61 | 7 | 0 | 6 | 47 | GAPS — features missing
Territory | 58 | 10 | 0 | 5 | 43 | GAPS — features missing
Calendar | 55 | 1 | 0 | 14 | 40 | GAPS — features missing
Consignment | 68 | 9 | 1 | 5 | 53 | GAPS — features missing
Accounts & Customers | 54 | 7 | 0 | 6 | 39 | GAPS — features missing
CIS & Credit Onboarding | 53 | 5 | 0 | 3 | 45 | GAPS — features missing
Mobile Field App | 68 | 0 | 0 | 7 | 61 | GAPS — features missing
Admin, Master Data & RBAC | 60 | 14 | 0 | 3 | 43 | GAPS — features missing
Reporting & Dashboards | 62 | 15 | 0 | 6 | 41 | GAPS — features missing
Pricing & Price Update | 42 | 0 | 0 | 24 | 18 | GAPS — features missing
Dealer Portal & Ordering | 56 | 3 | 0 | 14 | 39 | GAPS — features missing
Product Management & Catalog | 68 | 8 | 0 | 2 | 58 | GAPS — features missing
Digital Assets (DAM) | 60 | 6 | 0 | 2 | 52 | GAPS — features missing
Acumatica Integration | 54 | 0 | 0 | 19 | 35 | GAPS — features missing
Notifications | 58 | 12 | 0 | 7 | 38 | GAPS — features missing
Auth & Session | 61 | 6 | 0 | 1 | 54 | GAPS — features missing
Cross-Cutting Security, RBAC, Audit & PCI | 45 | 5 | 0 | 3 | 37 | GAPS — features missing
TOTAL | 1047 | 138 | 1 | 128 | 776

## GAPS (FAILED)
Gaps — unimplemented features reported as FAILED
Each case below cannot pass because the underlying capability is not implemented / not integrated. Marked FAILED per the gap-analysis instruction.
Test ID | Module | Priority | Test Scenario | Status | Gap — why it FAILS
LEAD-TC-050 | Leads | P2 | Voice-to-text note entry in the mobile app (not yet built) | FAIL | Feature NOT BUILT (backlog)
TRN-TC-011 | Training | P2 | Stale Outlook availability warning shown but does not block scheduling | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
TRN-TC-023 | Training | P1 | Scheduling/cancel attempts Outlook sync non-blocking; Pulse remains authoritative | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
TRN-TC-041 | Training | P1 | Sessions list shows a proof-required badge before execution | FAIL | Feature NOT BUILT (backlog)
TRN-TC-049 | Training | P1 | Certification completion records gift-card/demo-unit reward association | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
TRN-TC-060 | Training | P2 | Offline session completion queues locally and syncs on reconnect | FAIL | Parked — external dependency not available
TRN-TC-061 | Training | P2 | Voice-to-text available on the notes field during execution | FAIL | Feature NOT BUILT (backlog)
TER-TC-048 | Territory | P2 | State-level-coverage-only context banner is not yet present on the map | FAIL | Feature NOT BUILT (backlog)
TER-TC-049 | Territory | P2 | Filtered territory list with zero results shows no empty-state placeholder | FAIL | Feature NOT BUILT (backlog)
TER-TC-052 | Territory | P2 | Route plan stop model renders without provider-backed optimization | FAIL | Parked — external dependency not available
TER-TC-053 | Territory | P2 | GPS check-in geofence enforcement is parked | FAIL | Parked — external dependency not available
TER-TC-054 | Territory | P2 | Acumatica purchase/order overlay on the map is parked | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
CAL-TC-032 | Calendar | P1 | Scheduler modal source-of-truth info banner (not yet built) | FAIL | Feature NOT BUILT (backlog)
CAL-TC-033 | Calendar | P2 | Recurring schedule toggle creates single occurrence with recurrence intent in note (parked expansion) | FAIL | Parked — external dependency not available
CAL-TC-034 | Calendar | P0 | Connect Outlook via OAuth with PKCE state, single-use, 10-minute expiry | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-035 | Calendar | P0 | OAuth callback rejects missing/invalid/expired state and provider error | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-036 | Calendar | P0 | Outlook access/refresh tokens stored encrypted and never exposed in responses or logs | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-037 | Calendar | P0 | Auto-sync reflects newly scheduled discovery/training when policy auto-sync enabled | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-038 | Calendar | P0 | Manual 'Sync to Outlook' from detail rail creates/updates binding and shows timestamp | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-040 | Calendar | P0 | Manual sync of a lead/training record the actor cannot see is rejected (IDOR) | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-041 | Calendar | P1 | Sync rejects mismatched or unsupported event type for the source record | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-042 | Calendar | P0 | Rescheduling patches and cancelling removes the Outlook reflection | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-043 | Calendar | P0 | Teams online meeting created only for discovery/virtual training; join URL surfaced | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-044 | Calendar | P1 | Changing target calendar or meeting provider deletes and recreates the Outlook event | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-045 | Calendar | P1 | Disconnect removes all event bindings and the connection | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CAL-TC-046 | Calendar | P1 | Transient sync failure is audit-logged and stored on binding without interrupting the user | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CON-TC-050 | Consignment | P2 | Email/Graph delivery of consignment alerts remains parked (in-app only) | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CON-TC-051 | Consignment | P1 | Acumatica inventory read-model sync with last-sync timestamp and stale warning | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
CON-TC-052 | Consignment | P1 | Pulse links/references the Acumatica-posted PO but never posts it | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
CON-TC-053 | Consignment | P1 | Warehouse creation, TR transfer and receipt posting are Acumatica-owned (parked) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
CON-TC-060 | Consignment | P2 | Inventory-value and revenue KPIs are parked behind Acumatica truth | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACC-TC-024 | Accounts & Customers | P1 | Contact role uses governed catalogue (Primary/Owner-GM/Ordering/Billing/Accounting-AP/Technical) not free text | FAIL | Feature NOT BUILT (backlog)
ACC-TC-036 | Accounts & Customers | P0 | Attempt to submit a raw 13-19 digit card number must be rejected at the API boundary | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACC-TC-049 | Accounts & Customers | P2 | Malformed email and phone values on contacts (format validation gap) | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
ACC-TC-051 | Accounts & Customers | P0 | Acumatica customer ID, sync status badge and manual re-sync are parked behind the integration boundary | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACC-TC-052 | Accounts & Customers | P2 | Month-over-month sales-trend view depends on Acumatica order history and is parked | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACC-TC-053 | Accounts & Customers | P2 | Column-mapped CSV import of affinity member lists with dedup and result counts | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
CIS-TC-048 | CIS & Credit Onboarding | P0 | Hosted payment capture is blocked at the policy layer (provider parked / capture dormant) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
CIS-TC-049 | CIS & Credit Onboarding | P1 | Only tokenized vault references plus authorization state are stored (no raw instrument) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
CIS-TC-050 | CIS & Credit Onboarding | P2 | Card-on-file explanatory copy and progress-saved banner (open UI gaps) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
MOB-TC-022 | Mobile Field App | P1 | ROSE lines display SKU/barcode for reference with no camera scan button (scanning parked) | FAIL | Parked — external dependency not available
MOB-TC-045 | Mobile Field App | P0 | No silent device-side lead creation; commit goes only through governed CRM review (governed endpoint parked) | FAIL | Feature NOT BUILT (backlog)
MOB-TC-061 | Mobile Field App | P1 | Acumatica order placement / first-order account-create / authoritative pricing remain parked | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
MOB-TC-062 | Mobile Field App | P1 | Open account link from a field-activity review row (not yet built) | FAIL | Feature NOT BUILT (backlog)
MOB-TC-066 | Mobile Field App | P2 | Automatic AI writeback from voice notes/cards is parked; office approval required before activity | FAIL | Parked — external dependency not available
MOB-TC-067 | Mobile Field App | P2 | Calendar events shown via Pulse calendar API only; Outlook/Graph bi-directional sync parked | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
MOB-TC-068 | Mobile Field App | P2 | Field signals are in-app/derived only; push notifications, deep links, and background sync are parked | FAIL | Push notifications NOT IMPLEMENTED (no push provider)
ADM-TC-034 | Admin, Master Data & RBAC | P2 | Per-user permission override beyond assigned profile is not available | FAIL | Feature NOT BUILT (backlog)
ADM-TC-043 | Admin, Master Data & RBAC | P2 | Direct admin-panel CSV import for non-roster lists (brand/lead-source) not built | FAIL | Feature NOT BUILT (backlog)
ADM-TC-052 | Admin, Master Data & RBAC | P2 | Audit date-range filter is not built | FAIL | Feature NOT BUILT (backlog)
RPT-TC-024 | Reporting & Dashboards | P1 | Acumatica-sourced exec KPIs (YTD revenue, active accounts) remain parked, not fabricated | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
RPT-TC-035 | Reporting & Dashboards | P2 | Consignment inventory value by site is surfaced as a Parked placeholder (Acumatica inventory truth) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
RPT-TC-048 | Reporting & Dashboards | P2 | Order-based 'lost account' definition remains parked; only engagement-based staleness is built | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
RPT-TC-058 | Reporting & Dashboards | P1 | Drag-drop any-field selector, arbitrary sort, pre-save preview, and Priority Subjects tile section are not yet built | FAIL | Feature NOT BUILT (backlog)
RPT-TC-059 | Reporting & Dashboards | P0 | All revenue/YoY/Top-N revenue widgets are parked behind Acumatica/legacy migration | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
RPT-TC-061 | Reporting & Dashboards | P2 | Member-list penetration % and new-account-count widgets are not yet built (CRM-native, pending import/definition) | FAIL | Feature NOT BUILT (backlog)
PRC-TC-013 | Pricing & Price Update | P0 | Price class code accepts an arbitrary/unknown value (no master-list validation) | FAIL | Feature NOT BUILT (backlog)
PRC-TC-014 | Pricing & Price Update | P2 | Very long price class string is stored without a length cap | FAIL | Feature NOT BUILT (backlog)
PRC-TC-020 | Pricing & Price Update | P1 | No automatic default to generic A1 when price class is left blank | FAIL | Feature NOT BUILT (backlog)
PRC-TC-021 | Pricing & Price Update | P0 | Admin CRUD of residential price classes (create/edit/deactivate) | FAIL | Feature NOT BUILT (backlog)
PRC-TC-022 | Pricing & Price Update | P0 | USD and CAD price classes are maintained as separate, non-contaminating sets | FAIL | Feature NOT BUILT (backlog)
PRC-TC-023 | Pricing & Price Update | P0 | Wildcard rule definition, expansion to stock items, pinned overrides and % increase preview | FAIL | Feature NOT BUILT (backlog)
PRC-TC-024 | Pricing & Price Update | P0 | Admin must approve a SKU/current/new/%-change preview before publish | FAIL | Feature NOT BUILT (backlog)
PRC-TC-025 | Pricing & Price Update | P0 | Create named price-increase event with staggered per-class effective dates | FAIL | Feature NOT BUILT (backlog)
PRC-TC-026 | Pricing & Price Update | P1 | Draft routed to a named checker who can approve or send back before outputs | FAIL | Feature NOT BUILT (backlog)
PRC-TC-027 | Pricing & Price Update | P0 | Immutable, exportable price-change ledger (user/old/new/SKU/class/date) retained 7 years | FAIL | Feature NOT BUILT (backlog)
PRC-TC-028 | Pricing & Price Update | P1 | Query 'price of SKU X on date Y for class Z' from retained history | FAIL | Feature NOT BUILT (backlog)
PRC-TC-029 | Pricing & Price Update | P0 | Generate Acumatica price-worksheet CSV (CustomerPriceClassID, InventoryID, SalesPrice...) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
PRC-TC-030 | Pricing & Price Update | P0 | Generate Bold Commerce Shopify import CSV per applicable price class | FAIL | Parked — external dependency not available
PRC-TC-031 | Pricing & Price Update | P1 | Generate per-class Excel files and trigger a single bulk run of all outputs | FAIL | Feature NOT BUILT (backlog)
PRC-TC-032 | Pricing & Price Update | P1 | Generate branded per-class PDF price sheet with product images | FAIL | Parked — external dependency not available
PRC-TC-033 | Pricing & Price Update | P1 | Dealer views/downloads only their assigned price sheet; cannot see other classes | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
PRC-TC-034 | Pricing & Price Update | P0 | Dealer portal applies the dealer's assigned price class to their catalog view | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
PRC-TC-035 | Pricing & Price Update | P1 | System warns when a price-class entry exceeds the product base (highest) price | FAIL | Feature NOT BUILT (backlog)
PRC-TC-036 | Pricing & Price Update | P1 | Assigned price class displayed on the converted account/customer profile | FAIL | Feature NOT BUILT (backlog)
PRC-TC-037 | Pricing & Price Update | P2 | Instant-rebate flag shown on account profile for reference (no calculation) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
PRC-TC-038 | Pricing & Price Update | P0 | Dedicated pricing_admin / pricing_editor roles gate price-class/rule/event changes | FAIL | Feature NOT BUILT (backlog)
PRC-TC-039 | Pricing & Price Update | P1 | Acumatica-exported price matches dealer-portal price to 2dp; discrepancy logged/warned | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
PRC-TC-040 | Pricing & Price Update | P2 | Every CSV/PDF export logs user, timestamp, class, row count, file size, warnings | FAIL | Feature NOT BUILT (backlog)
PRC-TC-042 | Pricing & Price Update | P2 | No residential/commercial channel flag on price-class assignment | FAIL | Feature NOT BUILT (backlog)
DLR-TC-035 | Dealer Portal & Ordering | P0 | Credit-hold submit block (server-side) — seam present, enforcement parked | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-036 | Dealer Portal & Ordering | P0 | Credit-hold / past-due banner on dashboard with disabled ordering CTAs | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-037 | Dealer Portal & Ordering | P1 | Credit-hold/past-due change triggers configurable notifications to TM/RD/accounting | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-038 | Dealer Portal & Ordering | P0 | Account-context pricing from Acumatica price class shown at cart (parked) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-040 | Dealer Portal & Ordering | P0 | Requested delivery-date picker must NOT be exposed at checkout | FAIL | Feature NOT BUILT (backlog)
DLR-TC-041 | Dealer Portal & Ordering | P1 | Expedited shipping selection with estimated cost delta at checkout (parked) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-042 | Dealer Portal & Ordering | P2 | Gift-card / coupon code redemption at checkout (parked candidate) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-044 | Dealer Portal & Ordering | P1 | Order confirmation email to dealer and Dynamic AQS mailbox | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
DLR-TC-047 | Dealer Portal & Ordering | P0 | Tracking numbers with carrier deep-link and active-shipments status badges | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-048 | Dealer Portal & Ordering | P1 | Reorder from a prior order re-adds line items to cart and forces a new PO | FAIL | Feature NOT BUILT (backlog)
DLR-TC-049 | Dealer Portal & Ordering | P1 | YTD spend summary with monthly graph excludes shipping from rebate-eligible total | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
DLR-TC-050 | Dealer Portal & Ordering | P0 | Invoice list with status, PDF download, date-range filter, and summary totals | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-052 | Dealer Portal & Ordering | P2 | Payment terms (Net 30) and credit limit are visible in Account Center | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DLR-TC-054 | Dealer Portal & Ordering | P2 | Payment-decline alert on dashboard (parked candidate) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
PM-TC-065 | Product Management & Catalog | P0 | Dealer portal resolves account catalog view via active rule set and serves active snapshot with account price | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
PM-TC-066 | Product Management & Catalog | P1 | Dealer portal search/sort/filter, add-to-cart, locked billing, and past-due/credit-hold indicators | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
DAM-TC-059 | Digital Assets (DAM) | P2 | Legacy Widen URL redirect activation is parked (aliases stored as pending only) | FAIL | Parked — external dependency not available
DAM-TC-060 | Digital Assets (DAM) | P2 | Dedicated React Native digital-assets screen for TMs | FAIL | Feature NOT BUILT (backlog)
ACU-TC-019 | Acumatica Integration | P0 | PO received true-up records manual reference only; no Acumatica PO is posted | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-020 | Acumatica Integration | P0 | Inventory baseline recalculation remains Pulse-manual; not gated on a live Acumatica PO confirmation | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-021 | Acumatica Integration | P1 | PURPLE inventory adjustment updates Pulse manual baseline only; Acumatica post is parked | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-022 | Acumatica Integration | P1 | SAND exit closes site in Pulse with manual reconciliation; Acumatica settlement post parked | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-024 | Acumatica Integration | P0 | Consignment site detail does not show live Acumatica on-hand or in-transit transfer orders | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-025 | Acumatica Integration | P0 | First-order activation does NOT yet create an Acumatica customer; sync status stays parked | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-026 | Acumatica Integration | P0 | Duplicate first-order trigger must not create a second Acumatica customer (idempotency) | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-027 | Acumatica Integration | P0 | Failed customer creation retries up to 3x with back-off and surfaces a sync-error badge | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-029 | Acumatica Integration | P1 | Changing account legal name/address/contact/terms triggers an Acumatica PUT delta | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-030 | Acumatica Integration | P0 | Credit-hold badge on account detail is a placeholder; no live Acumatica CreditHold read | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-031 | Acumatica Integration | P0 | Dealer portal checkout is blocked with a clear message when account is on credit hold | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-032 | Acumatica Integration | P0 | Transition to credit-hold creates an OperationalAlert routed to assigned TM and RD | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
ACU-TC-033 | Acumatica Integration | P1 | Credit-hold sync uses 15-min polling default or push notifications when certified | FAIL | Push notifications NOT IMPLEMENTED (no push provider)
ACU-TC-036 | Acumatica Integration | P1 | Dealer portal prices resolve by the dealer's Acumatica price class; admin manual sync available | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-037 | Acumatica Integration | P1 | Checkout queries real-time Acumatica inventory; zero-quantity items show Out of stock | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-042 | Acumatica Integration | P1 | Account ERP Orders tab shows a placeholder; no live Acumatica order/invoice history | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-052 | Acumatica Integration | P1 | Concurrent first-order triggers must not race into two Acumatica customer creations | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
ACU-TC-053 | Acumatica Integration | P1 | Customer-creation payload requires mapped fields and valid contact email/phone formats | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
ACU-TC-054 | Acumatica Integration | P0 | No entity is written to Acumatica until $metadata schema and NAW.DAQS custom fields are documented | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
NOT-TC-050 | Notifications | P1 | Email delivery records a PREVIEW attempt and sends nothing until Graph creds land | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
NOT-TC-051 | Notifications | P1 | TM mobile push with deep-link payload for a newly assigned lead | FAIL | Push notifications NOT IMPLEMENTED (no push provider)
NOT-TC-052 | Notifications | P0 | Past-due (yellow) and credit-hold (red) notifications fan out to account users when the ERP flag toggles | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
NOT-TC-053 | Notifications | P1 | Generalized quiet-hours suppresses non-critical outbound channels in-window but still records in-app | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
NOT-TC-054 | Notifications | P1 | Low-urgency events roll into a daily digest instead of a per-event storm | FAIL | Email delivery NOT IMPLEMENTED (email channel / Microsoft Graph not connected)
NOT-TC-055 | Notifications | P2 | Routine notifications expire via TTL while audit/PO/credit items are retained permanently | FAIL | Feature NOT BUILT (backlog)
NOT-TC-058 | Notifications | P2 | Dealer card-declined / ACH-failed / free-shipping nudge surfaces with admin-editable copy | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)
AUTH-TC-061 | Auth & Session | P2 | Audit date-range filter (parked) over auth events | FAIL | Feature NOT BUILT (backlog)
SEC-TC-035 | Cross-Cutting Security, RBAC, Audit & PCI | P1 | Audit date-range filter is not yet available | FAIL | Feature NOT BUILT (backlog)
SEC-TC-041 | Cross-Cutting Security, RBAC, Audit & PCI | P2 | Per-user permission overrides are not built (fixed-role model only) | FAIL | Feature NOT BUILT (backlog)
SEC-TC-042 | Cross-Cutting Security, RBAC, Audit & PCI | P1 | Acumatica connectivity shows a warning state pending sandbox certification | FAIL | Depends on Acumatica ERP — NOT INTEGRATED (revenue/$/payment/pricing/order truth)

## Executed (live)
Live-executed checks — Web UI (21) + API (122)
Layer | Module | Check | Result | Detail
API | Accounts & Customers | ACC-TC-001 | PASS | Account list returns 200
API | Accounts & Customers | ACC-TC-010 | PASS | TM can read accounts (record-scoped)
API | Accounts & Customers | ACC-TC-002 | PASS | Account detail loads
API | Accounts & Customers | ACC-TC-003 | PASS | Unknown account -> not found
API | Accounts & Customers | ACC-TC-020 | PARTIAL | Sample account exposes no finance fields to evaluate masking
API | Accounts & Customers | ACC-TC-004 | PASS | Create account
API | Accounts & Customers | ACC-TC-005 | PASS | Account detail loads
API | Accounts & Customers | ACC-TC-011 | PARTIAL | SALES_BD_REP create-account access controlled (400)
WEB-UI | Accounts & Customers | Web page renders: /customers | PASS | Rendered correctly; saw ["Account","Pulse"]
API | Admin, Master Data & RBAC | ADM-TC-001 | PASS | Admin lists users
API | Admin, Master Data & RBAC | ADM-TC-002a | PASS | TERRITORY_MANAGER denied admin user list (default-deny)
API | Admin, Master Data & RBAC | ADM-TC-002b | PASS | FINANCE denied admin user list (default-deny)
API | Admin, Master Data & RBAC | ADM-TC-002c | PASS | SALES_BD_REP denied admin user list (default-deny)
API | Admin, Master Data & RBAC | ADM-TC-010 | PASS | System health readable by admin
API | Admin, Master Data & RBAC | ADM-TC-011 | PASS | Admin activity/audit log readable
API | Admin, Master Data & RBAC | ADM-TC-012 | PASS | Non-admin denied activity log
API | Admin, Master Data & RBAC | ADM-TC-020 | PASS | Admin reset-password
API | Admin, Master Data & RBAC | ADM-TC-021 | PASS | Admin update user
API | Admin, Master Data & RBAC | ADM-TC-022 | PASS | List roles
API | Admin, Master Data & RBAC | ADM-TC-023 | PASS | TM denied admin reset-password
WEB-UI | Admin, Master Data & RBAC | Web page renders: /admin/users | PASS | Rendered correctly; saw ["User","Pulse"]
WEB-UI | Admin, Master Data & RBAC | Web page renders: /admin/roles | PASS | Rendered correctly; saw ["Role","Pulse"]
WEB-UI | Admin, Master Data & RBAC | Web page renders: /admin/integrations | PASS | Rendered correctly; saw ["Integration","Pulse"]
API | Auth & Session | AUTH-TC-001 | PASS | Valid credentials returned a session + access token
API | Auth & Session | AUTH-TC-002 | PASS | Wrong password rejected
API | Auth & Session | AUTH-TC-003 | PASS | Unknown email rejected
API | Auth & Session | AUTH-TC-004 | PASS | Protected endpoint requires auth
API | Auth & Session | AUTH-TC-005 | PASS | Invalid/garbage token rejected
WEB-UI | Auth & Session | Login (web UI) as SUPER_ADMIN | PASS | Logged in, redirected to app
API | CIS & Credit Onboarding | CIS-TC-001 | PASS | FINANCE can read CIS finance queue
API | CIS & Credit Onboarding | CIS-TC-002 | PASS | TM denied CIS finance queue
API | CIS & Credit Onboarding | CIS-TC-005 | PASS | CIS link blocked before discovery (server-enforced gate)
API | CIS & Credit Onboarding | CIS-TC-006 | PASS | CIS link issued after discovery complete
API | CIS & Credit Onboarding | CIS-TC-007 | PASS | TM denied CIS link issuance
WEB-UI | Calendar | Web page renders: /calendar | PASS | Rendered correctly; saw ["Calendar","Pulse"]
API | Consignment | CON-TC-001 | PASS | Consignment sites 200
API | Consignment | CON-TC-002 | PASS | Consignment dashboard 200
API | Consignment | CON-TC-003 | PASS | Consignment ops 200
API | Consignment | CON-TC-010 | PASS | Create consignment site
API | Consignment | CON-TC-011 | PASS | Consignment site detail
API | Consignment | CON-TC-012 | PASS | Consignment readiness
API | Consignment | CON-TC-013 | PASS | Consignment documents
API | Consignment | CON-TC-014 | PASS | Create consignment audit
API | Consignment | CON-TC-031 | FAIL | DEFECT — consignment-site note ACCEPTED + stored a raw card number (HTTP 201); PCI guard not enforced on consignment notes in the deployed build (fix 327b6e9 not deployed). Leads/CIS reject the same input; consignment does not.
WEB-UI | Consignment | Web page renders: /consignment | PASS | Rendered correctly; saw ["Consignment","Pulse"]
API | Cross-Cutting Security, RBAC, Audit & PCI | SEC-TC-001 | PASS | All sampled protected endpoints require authentication
API | Cross-Cutting Security, RBAC, Audit & PCI | SEC-TC-002 | PASS | Default-deny: SALES_BD_REP denied admin module
API | Cross-Cutting Security, RBAC, Audit & PCI | SEC-TC-010 | PASS | PCI guard rejects Luhn-valid PAN in lead note
API | Cross-Cutting Security, RBAC, Audit & PCI | SEC-TC-011 | PASS | PCI guard does NOT false-positive on a 13-digit timestamp/order id
API | Cross-Cutting Security, RBAC, Audit & PCI | SEC-TC-020 | PASS | EXECUTIVE (read-only oversight) cannot mutate leads
API | Dealer Portal & Ordering | DLR-TC-001 | PASS | Internal role cannot access dealer portal /me
API | Dealer Portal & Ordering | DLR-TC-002 | PASS | Dealer /me catalog correctly unavailable to internal user (no dealer membership), got 400
WEB-UI | Dealer Portal & Ordering | Web page renders: /dealer/login | PASS | Rendered correctly; saw ["Dealer","Sign"]
API | Digital Assets (DAM) | DAM-TC-001 | PASS | DAM assets 200
API | Digital Assets (DAM) | DAM-TC-002 | PASS | DAM collections 200
API | Digital Assets (DAM) | DAM-TC-011 | PASS | DAM Widen import runs list
API | Digital Assets (DAM) | DAM-TC-012 | PASS | DAM Widen import preview endpoint reachable (405)
WEB-UI | Digital Assets (DAM) | Web page renders: /digital-assets | PASS | Rendered correctly; saw ["Digital Assets","Library"]
WEB-UI | Digital Assets (DAM) | Web page renders: /digital-assets?tab=migration | PASS | Rendered correctly; saw ["Migration Review","Widen"]
API | Leads | LEAD-TC-005 | PASS | Authorized user created a manual lead
API | Leads | LEAD-TC-006a | PASS | TERRITORY_MANAGER correctly denied lead creation (default-deny)
API | Leads | LEAD-TC-006b | PASS | REGIONAL_DIRECTOR correctly denied lead creation (default-deny)
API | Leads | LEAD-TC-006c | PASS | FINANCE correctly denied lead creation (default-deny)
API | Leads | LEAD-TC-007 | PASS | Invalid email rejected at intake
API | Leads | LEAD-TC-008 | PASS | Invalid phone (too few digits) rejected
API | Leads | LEAD-TC-009 | PASS | Missing company rejected
API | Leads | LEAD-TC-031 | PASS | PCI: raw card number in lead note rejected
API | Leads | LEAD-TC-040 | PASS | Lead list returns items
API | Leads | LEAD-TC-041 | PASS | Non-existent lead returns not-found/forbidden
API | Leads | LEAD-TC-053 | PASS | Duplicate detection: 2nd lead with same phone is blocked pending resolution (400)
API | Leads | LEAD-TC-008b | PASS | 7-digit phone (lower boundary) accepted
API | Leads | LEAD-TC-008c | PASS | 16-digit phone (over boundary) rejected
API | Leads | LEAD-TC-050 | PASS | Special chars / SQL-ish input handled without server error
API | Leads | LEAD-TC-051 | PASS | Oversized field handled gracefully (400)
API | Leads | LEAD-TC-052 | PASS | Pagination limit honoured (<=2 items)
API | Leads | LEAD-TC-020 | PASS | Discovery scheduled
API | Leads | LEAD-TC-021 | PASS | Discovery completed (lead advanced)
API | Leads | LEAD-TC-002b | PASS | Create lead (deep fixture)
API | Leads | LEAD-TC-060 | PASS | Add lead contact
API | Leads | LEAD-TC-061 | PASS | List lead contacts
API | Leads | LEAD-TC-062 | PASS | Log activity note
API | Leads | LEAD-TC-070 | PASS | Lead readiness loads
API | Leads | LEAD-TC-072 | PASS | Lead readiness blockers loads
API | Leads | LEAD-TC-073 | PASS | Log initial contact
API | Leads | LEAD-TC-074 | PASS | Lead search filter
API | Leads | LEAD-TC-075 | PASS | Lead stage filter
API | Leads | LEAD-TC-076 | PASS | TM can view leads (scoped)
WEB-UI | Leads | Leads: list renders rows | PASS | 104 lead rows/links present
WEB-UI | Leads | Web page renders: /leads | PASS | Rendered correctly; saw ["Lead","QA-HVAC"]
API | Notifications | NOT-TC-001 | PASS | Notifications inbox list 200
API | Notifications | NOT-TC-002 | PASS | Notifications unread count 200
API | Notifications | NOT-TC-003 | PASS | Notifications preferences 200
API | Notifications | NOT-TC-010 | PASS | Admin can read routing rules
API | Notifications | NOT-TC-011 | PASS | Routing rules access for TM controlled (403)
API | Notifications | NOT-TC-020 | PASS | Mark notifications read
API | Notifications | NOT-TC-021 | PARTIAL | 400: A valid notification category is required.
API | Notifications | NOT-TC-022 | PASS | Create notification routing rule
API | Notifications | NOT-TC-023 | PASS | Delete routing rule
API | Notifications | NOT-TC-024 | PASS | TM denied routing-rule creation (admin-gated)
WEB-UI | Notifications | Web page renders: /notifications | PASS | Rendered correctly; saw ["Notifications"]
WEB-UI | Notifications | Web page renders: /settings/notifications/routing | PASS | Rendered correctly; saw ["Recipient"]
WEB-UI | Notifications | Web page renders: /settings/notifications | PASS | Rendered correctly; saw ["Notification preferences"]
API | Product Management & Catalog | PM-TC-001 | PASS | Product families 200
API | Product Management & Catalog | PM-TC-002 | PASS | Product categories 200
API | Product Management & Catalog | PM-TC-003 | PASS | Product rule sets 200
API | Product Management & Catalog | PM-TC-004 | PASS | Product catalog views 200
API | Product Management & Catalog | PM-TC-010 | PASS | Create product family
API | Product Management & Catalog | PM-TC-011 | PASS | Create product category
API | Product Management & Catalog | PM-TC-012 | PASS | SALES_BD_REP denied catalog manage
WEB-UI | Product Management & Catalog | Web page renders: /product-management | PASS | Rendered correctly; saw ["Product","Pulse"]
API | Reporting & Dashboards | RPT-TC-001 | PASS | Lead dashboard returns 200 for SUPER_ADMIN
API | Reporting & Dashboards | RPT-TC-002 | PASS | Training dashboard returns 200 for SUPER_ADMIN
API | Reporting & Dashboards | RPT-TC-003 | PASS | Executive dashboard returns 200 for SUPER_ADMIN
API | Reporting & Dashboards | RPT-TC-020 | PASS | EXECUTIVE can view executive dashboard
API | Reporting & Dashboards | RPT-TC-021 | PASS | TM denied executive dashboard (reports.executive gate)
API | Reporting & Dashboards | RPT-TC-039 | PASS | Stale/neglected accounts report 200
API | Reporting & Dashboards | RPT-TC-003b | PASS | Threshold settings readable
API | Reporting & Dashboards | RPT-TC-022b | PASS | TM threshold-settings access controlled (200)
API | Reporting & Dashboards | RPT-TC-064 | PASS | List report definitions
API | Reporting & Dashboards | RPT-RUN-lead_funnel | PASS | Run ad-hoc report lead_funnel
API | Reporting & Dashboards | RPT-RUN-training_compliance | PASS | Run ad-hoc report training_compliance
API | Reporting & Dashboards | RPT-RUN-consignment_audit_status | PASS | Run ad-hoc report consignment_audit_status
API | Reporting & Dashboards | RPT-RUN-field_activity | PASS | Run ad-hoc report field_activity
WEB-UI | Reporting & Dashboards | Reports: dashboard Export control present (CSV/Excel/PDF) | PASS | Export button rendered on dashboard
WEB-UI | Reporting & Dashboards | Web page renders: /reports | PASS | Rendered correctly; saw ["Reports","Export"]
API | Territory | TER-TC-001 | PASS | Territory list 200
API | Territory | TER-TC-002 | PASS | Territory regions 200
API | Territory | TER-TC-003 | PASS | Territory map 200
API | Territory | TER-TC-004 | PASS | Territory dashboard 200
API | Territory | TER-TC-010 | PASS | TM can read territories
API | Territory | TER-TC-020 | PASS | Territory assignable users
API | Territory | TER-TC-021 | PASS | Territory policy
API | Territory | TER-TC-023 | PASS | Territory shipping centers
WEB-UI | Territory | Web page renders: /territories | PASS | Rendered correctly; saw ["Territor","Pulse"]
WEB-UI | Territory | Web page renders: /territory_map | PASS | Rendered correctly; saw ["Pulse"]
API | Training | TRN-TC-001 | PASS | Training sessions 200
API | Training | TRN-TC-002 | PASS | Training overview 200
API | Training | TRN-TC-003 | PASS | Training catalog 200
API | Training | TRN-TC-004 | PASS | Training trainers 200
API | Training | TRN-TC-010 | PASS | TRAINING_OPS can read sessions
API | Training | TRN-TC-020 | PARTIAL | schedule session -> 400: Training type not found
API | Training | TRN-TC-023 | PASS | FINANCE denied training.schedule
WEB-UI | Training | Web page renders: /training | PASS | Rendered correctly; saw ["Training","Pulse"]