## Coverage Summary
Report Generated | 2026-03-31
SCOPE COVERAGE METRICS
Metric | Value | Note
Structured Functional Requirements (FRs) | 488 | Parsed from active PRDs that use FR tables
Mapped structured FRs in current core baseline | 305 | FRs still covered by the reduced 1603-SP delivery baseline, now with migration waves called out in the WBS and migration register
Deferred structured FRs | 183 | Known in PRDs but intentionally outside the slimmed build baseline
Direct high-confidence FR mappings retained | 279 | Mapped to kept WBS rows
Module-level heuristic FR mappings retained | 26 | Still mapped within kept modules but should be reviewed

## FR-to-WBS Traceability
FR-to-WBS Traceability
FR ID | Source PRD | WBS Module | Requirement | WBS Row # | WBS Epic | WBS Story | Status
FR-AN-001 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | New Lead Assigned | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-002 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Lead SLA Breach | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-003 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | CIS Submitted | 38 | Alert Engine | Create one notification framework | MODULE_MAPPED
FR-AN-004 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | CIS Finance Submitted | 38 | Alert Engine | Create one notification framework | MODULE_MAPPED
FR-AN-005 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Credit Decision Made | 67 | Alert Engine | Create one notification framework | MAPPED
FR-AN-006 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Consignment Audit Due |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-007 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Consignment Audit Overdue |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-008 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | PO Clock Warning |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-009 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Training Reminder |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-010 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Customer At-Risk |  | Communication Hub | Centralize email context | DEFERRED_SCOPE
FR-AN-011 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Lead Stage Regression | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-012 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Training No-Show |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-013 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Certification Expiring | 38 | Alert Engine | Create one notification framework | MODULE_MAPPED
FR-AN-014 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Sync Error |  | Outlook Integration | Stop double handling email | DEFERRED_SCOPE
FR-AN-015 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Portal Order Placed | 67 | Alert Engine | Create one notification framework | MAPPED
FR-AN-016 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Onboarding Step Complete |  | Templates & Campaigns | Standardize outbound communication | DEFERRED_SCOPE
FR-AN-017 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Territory Reassignment | 67 | Alert Engine | Create one notification framework | MODULE_MAPPED
FR-AN-018 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Report Ready | 38 | Alert Engine | Create one notification framework | MODULE_MAPPED
FR-AN-019 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Discrepancy Case Created | 39 | Alert Platform Readiness | Prove the alert engine before consumers scale | MODULE_MAPPED
FR-AN-020 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | System Maintenance | 38 | Alert Engine | Create one notification framework | MODULE_MAPPED
FR-AN-021 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Stage Transition | 39 | Alert Platform Readiness | Prove the alert engine before consumers scale | MODULE_MAPPED
FR-AN-022 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Credit Hold / Past Due Status | 136 | Credit & Collections Alerts | Make financial blockers visible | MAPPED
FR-AN-023 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Mobile Territory Assignment | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-024 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Order Submitted |  | Order Behavior Alerts | Spot purchasing anomalies | DEFERRED_SCOPE
FR-AN-025 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Alert rule engine | 39 | Alert Platform Readiness | Prove the alert engine before consumers scale | MAPPED
FR-AN-026 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | In-app notification center | 136 | Credit & Collections Alerts | Make financial blockers visible | MAPPED
FR-AN-027 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Notification mark as read |  | Lead Intake Operations | Enable all inbound channels | DEFERRED_SCOPE
FR-AN-028 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Email notifications |  | Communication Hub | Centralize email context | DEFERRED_SCOPE
FR-AN-029 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Mobile push notifications | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-030 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Notification preferences | 67 | Alert Engine | Create one notification framework | MAPPED
FR-AN-031 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Do-not-disturb schedule | 39 | Alert Platform Readiness | Prove the alert engine before consumers scale | MAPPED
FR-AN-032 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Daily digest option | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-033 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Escalation rules | 39 | Alert Platform Readiness | Prove the alert engine before consumers scale | MAPPED
FR-AN-034 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Acknowledgment tracking | 38 | Alert Engine | Create one notification framework | MAPPED
FR-AN-035 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Notification audit trail |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-036 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Batch notifications | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-037 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Deep link from notification | 68 | Lead Alerts | Notify teams about inbound opportunity | MAPPED
FR-AN-038 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Admin alert configuration | 67 | Alert Engine | Create one notification framework | MAPPED
FR-AN-039 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Template management |  | Escalation Management | Govern exception handling | DEFERRED_SCOPE
FR-AN-040 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Unified communication view |  | Communication Hub | Centralize email context | DEFERRED_SCOPE
FR-AN-041 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Communication search |  | Templates & Campaigns | Standardize outbound communication | DEFERRED_SCOPE
FR-AN-042 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Resend capability | 67 | Alert Engine | Create one notification framework | MAPPED
FR-AN-043 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Communication metrics |  | Templates & Campaigns | Standardize outbound communication | DEFERRED_SCOPE
FR-AN-044 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Email context linking |  | Communication Hub | Centralize email context | DEFERRED_SCOPE
FR-AN-045 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Training inactivity red flag |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-046 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Consignment operational alerts |  | Training & Consignment Alerts | Keep recurring obligations on track | DEFERRED_SCOPE
FR-AN-047 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Exception report delivery | 38 | Alert Engine | Create one notification framework | MAPPED
FR-AN-048 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Touchpoint completeness |  | Communication Hub | Centralize email context | DEFERRED_SCOPE
FR-AN-049 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Territory-aware recipients |  | Dealer & Internal Sharing | Keep internal teams aware of dealer financial issues | DEFERRED_SCOPE
FR-AN-050 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Consignment cadence reminders | 39 | Alert Platform Readiness | Prove the alert engine before consumers scale | MAPPED
FR-AN-051 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication, Notifications & Alerts | Order-activity monitoring baseline |  | Order Behavior Alerts | Spot purchasing anomalies | DEFERRED_SCOPE
FR-CIS-001 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Generate unique CIS link |  | Pipeline Integration | Keep onboarding visible | DEFERRED_SCOPE
FR-CIS-002 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Digital CIS form — company info section | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-003 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Digital CIS form — contact sections | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-004 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Digital CIS form — business registration | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-005 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Digital CIS form — payment method | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-006 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Digital CIS form — resale certificate | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-007 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | E-signature capture | 51 | Digital CIS | Replace paper onboarding | MAPPED
FR-CIS-008 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Save as draft | 49 | CIS Design and Capture | Digitize the CIS experience | MODULE_MAPPED
FR-CIS-009 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Form validation | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-010 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Canada form variant | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-011 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Scanned CIS upload | 51 | Digital CIS | Replace paper onboarding | MAPPED
FR-CIS-012 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | CIS status tracking |  | Pipeline Integration | Keep onboarding visible | DEFERRED_SCOPE
FR-CIS-013 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | CIS auto-populate from lead | 75 | Onboarding Data Flow | Reuse submitted onboarding data | MAPPED
FR-CIS-014 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | CIS expiration |  | Onboarding Controls | Standardize post-CIS activation | DEFERRED_SCOPE
FR-CIS-015 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | CIS PDF generation | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-016 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Finance queue view | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-017 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | CIS review detail | 49 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-018 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Approve with credit terms | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-019 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Decline with reason | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-020 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Conditional approval | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-021 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Request additional information | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-022 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Finance SLA tracking | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-023 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Finance decision audit trail | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-024 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Finance dashboard | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-025 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Credit line tiers | 74 | Onboarding Controls | Standardize post-CIS activation | MAPPED
FR-CIS-026 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Auto-generate onboarding checklist | 76 | Onboarding Control | Standardize post-CIS activation | MAPPED
FR-CIS-027 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Portal access provisioning | 76 | Onboarding Control | Standardize post-CIS activation | MAPPED
FR-CIS-028 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Pricing profile assignment | 76 | Onboarding Control | Standardize post-CIS activation | MAPPED
FR-CIS-029 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Welcome email | 76 | Onboarding Control | Standardize post-CIS activation | MODULE_MAPPED
FR-CIS-030 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | 3 WebEx training sessions |  | Outlook Integration | Synchronize training events bidirectionally with Outlook | DEFERRED_SCOPE
FR-CIS-031 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Training scheduling |  | Outlook Integration | Synchronize training events bidirectionally with Outlook | DEFERRED_SCOPE
FR-CIS-032 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Training completion tracking |  | Outlook Integration | Synchronize training events bidirectionally with Outlook | DEFERRED_SCOPE
FR-CIS-033 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Onboarding progress percentage | 50 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-034 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Account readiness checklist | 76 | Onboarding Control | Standardize post-CIS activation | MAPPED
FR-CIS-035 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Onboarding SLA | 76 | Onboarding Control | Standardize post-CIS activation | MAPPED
FR-CIS-036 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Consignment interest capture | 51 | Digital CIS | Replace paper onboarding | MAPPED
FR-CIS-037 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | Onboarding handoff to TM | 50 | CIS Design and Capture | Digitize the CIS experience | MAPPED
FR-CIS-038 | CIS_CREDIT_ONBOARDING_PRD.md | CIS, Credit & Onboarding Workflow | First-order readiness gate | 76 | Onboarding Control | Standardize post-CIS activation | MAPPED
FR-CSG-001 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Consignment enrollment from lead/customer | 105 | Consignment Enrollment | Launch and manage the program correctly | MAPPED
FR-CSG-002 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Consignment agreement management | 105 | Consignment Enrollment | Launch and manage the program correctly | MAPPED
FR-CSG-003 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Agreement template | 105 | Consignment Enrollment | Launch and manage the program correctly | MODULE_MAPPED
FR-CSG-004 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Enrollment approval workflow | 105 | Consignment Enrollment | Launch and manage the program correctly | MAPPED
FR-CSG-005 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Consignment site creation | 109 | Site Setup | Onboard new consignment locations correctly | MAPPED
FR-CSG-006 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Initial inventory deployment | 107 | Initial Verification | Establish starting inventory truth | MAPPED
FR-CSG-007 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | BLUE form workflow |  | Site Operations | Manage inventory movement accurately | DEFERRED_SCOPE
FR-CSG-008 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Disenrollment workflow |  | Program Exit | Manage program termination cleanly | DEFERRED_SCOPE
FR-CSG-009 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Consignment site list | 104 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-010 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Site status tracking | 113 | Operational Readiness Gates | Prove consignment foundations before downstream automation | MAPPED
FR-CSG-011 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | 90-day audit cycle scheduling | 111 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-012 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Audit due alerts | 111 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-013 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Overdue audit escalation | 111 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-014 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | ROSE Step 1: Review | 106 | Consignment Onboarding | Standardize new consignment setup | MAPPED
FR-CSG-015 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | ROSE Step 2: Observe | 106 | Consignment Onboarding | Standardize new consignment setup | MAPPED
FR-CSG-016 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | ROSE Step 3: Scan | 106 | Consignment Onboarding | Standardize new consignment setup | MAPPED
FR-CSG-017 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | ROSE Step 4: Evaluate | 106 | Consignment Onboarding | Standardize new consignment setup | MAPPED
FR-CSG-018 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | ROSE Step 5: Exceptions | 106 | Consignment Onboarding | Standardize new consignment setup | MAPPED
FR-CSG-019 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | ROSE Step 6: Report | 106 | Consignment Onboarding | Standardize new consignment setup | MAPPED
FR-CSG-020 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | ROSE Step 7: Settle | 106 | Consignment Onboarding | Standardize new consignment setup | MAPPED
FR-CSG-021 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Audit line items | 113 | Operational Readiness Gates | Prove consignment foundations before downstream automation | MAPPED
FR-CSG-022 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Barcode scanning (mobile) |  | Barcode Readiness | Prepare for future scanning | DEFERRED_SCOPE
FR-CSG-023 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Audit photos |  | Mobile Audit | Support audits in the field | DEFERRED_SCOPE
FR-CSG-024 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Audit attestation | 111 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-025 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Offline audit support | 111 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-026 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Reconciliation algorithm | 112 | Reconciliation Workflow | Replace Excel and Dropbox reconciliation | MAPPED
FR-CSG-027 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Discrepancy case creation | 109 | Site Setup | Onboard new consignment locations correctly | MAPPED
FR-CSG-028 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Discrepancy resolution workflow |  | Cycle Governance | Govern non-standard consignment resolution paths | DEFERRED_SCOPE
FR-CSG-029 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | PO follow-up — 5 business day clock |  | PO Recovery | Track missing inventory follow-up | DEFERRED_SCOPE
FR-CSG-030 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | PO clock alerts |  | PO Recovery | Track missing inventory follow-up | DEFERRED_SCOPE
FR-CSG-031 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | PO received confirmation |  | Site Operations | Manage inventory movement accurately | DEFERRED_SCOPE
FR-CSG-032 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | PO overdue escalation |  | PO Recovery | Track missing inventory follow-up | DEFERRED_SCOPE
FR-CSG-033 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Inventory baseline update |  | Portfolio Analytics | Make the program measurable | DEFERRED_SCOPE
FR-CSG-034 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Acumatica inventory sync |  | Site Operations | Manage inventory movement accurately | DEFERRED_SCOPE
FR-CSG-035 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | PO generation to Acumatica | 109 | Site Setup | Onboard new consignment locations correctly | MAPPED
FR-CSG-036 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | BLUE cycle |  | Cycle Governance | Govern non-standard consignment resolution paths | DEFERRED_SCOPE
FR-CSG-037 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | PURPLE cycle |  | Cycle Governance | Govern non-standard consignment resolution paths | DEFERRED_SCOPE
FR-CSG-038 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | SAND cycle |  | Cycle Governance | Govern non-standard consignment resolution paths | DEFERRED_SCOPE
FR-CSG-039 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Cycle type tracking |  | Cycle Governance | Govern non-standard consignment resolution paths | DEFERRED_SCOPE
FR-CSG-040 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Cycle scheduling rules |  | Cycle Governance | Govern non-standard consignment resolution paths | DEFERRED_SCOPE
FR-CSG-041 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Audit and reconciliation are separate states | 113 | Operational Readiness Gates | Prove consignment foundations before downstream automation | MAPPED
FR-CSG-042 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | PO clock starts only after true-up review | 152 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-043 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Near-real-time warehouse context | 108 | Location Master | Bring real consignment locations into CRM | MAPPED
FR-CSG-044 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Acumatica-first warehouse creation | 109 | Site Setup | Onboard new consignment locations correctly | MAPPED
FR-CSG-045 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Role-filtered consignment dashboards | 113 | Operational Readiness Gates | Prove consignment foundations before downstream automation | MAPPED
FR-CSG-046 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Warehouse readiness snapshot | 113 | Operational Readiness Gates | Prove consignment foundations before downstream automation | MAPPED
FR-CSG-047 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | BLUE form baseline activation | 107 | Initial Verification | Establish starting inventory truth | MAPPED
FR-CSG-048 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Variance drilldown |  | Portfolio Analytics | Make the program measurable | DEFERRED_SCOPE
FR-CSG-049 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Manual count remains required |  | Mobile Audit | Support audits in the field | DEFERRED_SCOPE
FR-CSG-050 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Customer account indicator |  | Site Operations | Manage inventory movement accurately | DEFERRED_SCOPE
FR-CSG-051 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Shared mailbox operating queue | 104 | Audit Cycle | Enforce the 90-day operating rhythm | MAPPED
FR-CSG-052 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | BLUE/PURPLE document semantics |  | Cycle Governance | Govern non-standard consignment resolution paths | DEFERRED_SCOPE
FR-CSG-053 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Phase 1 on-site audit mode | 113 | Operational Readiness Gates | Prove consignment foundations before downstream automation | MAPPED
FR-CSG-054 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | Formal exit workflow controls |  | Program Exit | Manage program termination cleanly | DEFERRED_SCOPE
FR-CSG-055 | CONSIGNMENT_MANAGEMENT_PRD.md | Consignment Management | TM mobile audit and back-office reconciliation split | 113 | Operational Readiness Gates | Prove consignment foundations before downstream automation | MAPPED
FR-CA-001 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer creation on first order | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-002 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Lead remains lead until first order | 81 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-003 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer 360 workspace | 54 | Customer 360 | Model the full customer account | MAPPED
FR-CA-004 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Account information section | 54 | Customer 360 | Model the full customer account | MAPPED
FR-CA-005 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer lifecycle status | 84 | Customer Workspace | Make the account model operable at scale | MAPPED
FR-CA-006 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | At-risk flag | 84 | Customer Workspace | Make the account model operable at scale | MAPPED
FR-CA-007 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer search | 84 | Customer Workspace | Make the account model operable at scale | MAPPED
FR-CA-008 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer list view | 84 | Customer Workspace | Make the account model operable at scale | MAPPED
FR-CA-009 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer edit | 54 | Customer 360 | Model the full customer account | MAPPED
FR-CA-010 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer notes | 78 | Activity Management | Preserve field and service interactions | MAPPED
FR-CA-011 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Data from lead carried forward | 55 | Customer 360 | Model the full customer account | MAPPED
FR-CA-012 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Source lead reference | 81 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-013 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Acumatica customer ID | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-014 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Sync status indicator | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-015 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Customer merge |  | Customer Data Quality | Resolve duplicates without losing history | DEFERRED_SCOPE
FR-CA-016 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Multiple contacts per customer | 54 | Customer 360 | Model the full customer account | MAPPED
FR-CA-017 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact roles | 53 | Contact Management | Implement contact hierarchy and role ordering | MAPPED
FR-CA-018 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact fields | 53 | Contact Management | Implement contact hierarchy and role ordering | MAPPED
FR-CA-019 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact-to-portal user link |  | Customer Account Model | Build the operational customer view | DEFERRED_SCOPE
FR-CA-020 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact hierarchy display | 53 | Contact Management | Implement contact hierarchy and role ordering | MAPPED
FR-CA-021 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact sync with Acumatica | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-022 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact deactivation | 53 | Contact Management | Implement contact hierarchy and role ordering | MAPPED
FR-CA-023 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Training attendance linking | 53 | Contact Management | Implement contact hierarchy and role ordering | MODULE_MAPPED
FR-CA-024 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact search across customers | 53 | Contact Management | Implement contact hierarchy and role ordering | MAPPED
FR-CA-025 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Contact import from CIS | 53 | Contact Management | Implement contact hierarchy and role ordering | MAPPED
FR-CA-026 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Multiple locations per customer | 54 | Customer 360 | Model the full customer account | MAPPED
FR-CA-027 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Location fields | 56 | Multi-Location Management | Build parent-child location hierarchy and shared account rollups | MAPPED
FR-CA-028 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Warehouse assignment | 56 | Multi-Location Management | Build parent-child location hierarchy and shared account rollups | MAPPED
FR-CA-029 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | TM assignment per location | 56 | Multi-Location Management | Build parent-child location hierarchy and shared account rollups | MAPPED
FR-CA-030 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Billing vs shipping address | 54 | Customer 360 | Model the full customer account | MAPPED
FR-CA-031 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Location map display | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-032 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Consignment site linking | 54 | Customer 360 | Model the full customer account | MODULE_MAPPED
FR-CA-033 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Parent/child account hierarchy | 56 | Multi-Location Management | Build parent-child location hierarchy and shared account rollups | MAPPED
FR-CA-034 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Dealer group resolution algorithm |  | Customer Data Quality | Resolve duplicates without losing history | DEFERRED_SCOPE
FR-CA-035 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Price class assignment from dealer group | 55 | Customer 360 | Model the full customer account | MAPPED
FR-CA-036 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Dealer group display on Customer 360 | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-037 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Dealer group override |  | Customer Account Model | Build the operational customer view | DEFERRED_SCOPE
FR-CA-038 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Price class history |  | Auditability | Protect customer history | DEFERRED_SCOPE
FR-CA-039 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Affinity group management | 55 | Customer 360 | Model the full customer account | MAPPED
FR-CA-040 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Ownership group management | 55 | Customer 360 | Model the full customer account | MAPPED
FR-CA-041 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Orders tab on Customer 360 | 54 | Customer 360 | Model the full customer account | MAPPED
FR-CA-042 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Invoices tab |  | Customer Workspace | Surface ERP context where teams actually work | DEFERRED_SCOPE
FR-CA-043 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Shipments tab |  | Customer Workspace | Surface ERP context where teams actually work | DEFERRED_SCOPE
FR-CA-044 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Payments tab |  | Customer Workspace | Surface ERP context where teams actually work | DEFERRED_SCOPE
FR-CA-045 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Statement summary | 82 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-046 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Read-only financial data |  | Customer Workspace | Surface ERP context where teams actually work | DEFERRED_SCOPE
FR-CA-047 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Sync freshness indicator | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-CA-048 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer, Account, Contact & Multi-Location Management | Manual sync trigger | 80 | Customer Activation | Control the ERP activation gate | MAPPED
FR-DA-001 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset upload | 149 | Asset Workflow | Govern file uploads and approvals | MAPPED
FR-DA-002 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset metadata |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-003 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset versioning | 149 | Asset Workflow | Govern file uploads and approvals | MAPPED
FR-DA-004 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset search |  | Metadata & Filtering | Make assets usable at scale | DEFERRED_SCOPE
FR-DA-005 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset preview | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-006 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset download |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-007 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Stable asset URLs | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-008 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Folder organization |  | Metadata & Filtering | Make assets usable at scale | DEFERRED_SCOPE
FR-DA-009 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset sharing |  | Asset Sharing | Send the right file from the right context | DEFERRED_SCOPE
FR-DA-010 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset usage tracking |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-011 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Bulk upload | 149 | Asset Workflow | Govern file uploads and approvals | MAPPED
FR-DA-012 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Drag-and-drop upload | 149 | Asset Workflow | Govern file uploads and approvals | MAPPED
FR-DA-013 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Image optimization | 149 | Asset Workflow | Govern file uploads and approvals | MODULE_MAPPED
FR-DA-014 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Storage quota monitoring |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-015 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset archive/delete |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-016 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Link assets to product presentations | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-017 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset type per product | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-018 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Dealer group scoping | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-019 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Brand label scoping |  | Metadata & Filtering | Make assets usable at scale | DEFERRED_SCOPE
FR-DA-020 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Wrong-brand warning | 149 | Asset Workflow | Govern file uploads and approvals | MAPPED
FR-DA-021 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Go-live asset validation | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-022 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Product page asset display | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-023 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Dealer-safe downloads |  | Dealer Downloads | Expose branded collateral in the portal | DEFERRED_SCOPE
FR-DA-024 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Downloads page |  | Dealer Downloads | Expose branded collateral in the portal | DEFERRED_SCOPE
FR-DA-025 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Branded export packs |  | Asset Variant Governance | Support Widen-like branded asset families in-scope | DEFERRED_SCOPE
FR-DA-026 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset access audit |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-027 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Curated collections |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-028 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Mobile asset access |  | Asset Sharing | Send the right file from the right context | DEFERRED_SCOPE
FR-DA-029 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Dropbox import tool | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-030 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Widen coexistence | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-031 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Widen import tool |  | Legacy File Migration | Preserve legacy document history | DEFERRED_SCOPE
FR-DA-032 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Duplicate detection | 149 | Asset Workflow | Govern file uploads and approvals | MODULE_MAPPED
FR-DA-033 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Stable shared-link behavior | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-034 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Multi-site asset reuse | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-035 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Portal-style collections |  | Dealer Downloads | Expose branded collateral in the portal | DEFERRED_SCOPE
FR-DA-036 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Quick search and send |  | Asset Sharing | Send the right file from the right context | DEFERRED_SCOPE
FR-DA-037 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Better-than-folder UX |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-038 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Mobile-friendly asset access |  | Asset Sharing | Send the right file from the right context | DEFERRED_SCOPE
FR-DA-039 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Internal admin app plus external portal split |  | Dealer Downloads | Expose branded collateral in the portal | DEFERRED_SCOPE
FR-DA-040 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Asset-type filtering baseline |  | Metadata & Filtering | Make assets usable at scale | DEFERRED_SCOPE
FR-DA-041 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Mandatory ingest metadata validation |  | Asset Repository | Replace scattered file hunts | DEFERRED_SCOPE
FR-DA-042 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Link-first single source of truth | 148 | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | MAPPED
FR-DA-043 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Digital Assets & Document Handling | Access-mode separation | 149 | Asset Workflow | Govern file uploads and approvals | MAPPED
FR-FA-001 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Microsoft Entra ID SSO for internal users | 13 | Identity & Access | Secure internal and dealer access | MAPPED
FR-FA-002 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Database-backed auth for dealer portal users | 36 | Security & Compliance | Separate internal workflow data from dealer visibility | MAPPED
FR-FA-003 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | JWT token issuance | 9 | Environments & Delivery | Operate reliable delivery environments | MODULE_MAPPED
FR-FA-004 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Session management |  | Resilience & Trust | Manage database growth for high-volume tables | DEFERRED_SCOPE
FR-FA-005 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Password policy (dealer) | 13 | Identity & Access | Secure internal and dealer access | MAPPED
FR-FA-006 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Account lockout | 9 | Environments & Delivery | Operate reliable delivery environments | MODULE_MAPPED
FR-FA-007 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Password reset flow | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-008 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | MFA for admin roles | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-009 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | SSO role mapping | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-010 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Session timeout | 14 | Identity & Access | Enforce role-based permissions | MODULE_MAPPED
FR-FA-011 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | 10 role groups | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-012 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Module-level permissions | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-013 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Record-level scoping | 15 | Identity & Access | Enforce record-scope hierarchical filtering | MAPPED
FR-FA-014 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Role assignment | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-015 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Route guards | 36 | Security & Compliance | Separate internal workflow data from dealer visibility | MAPPED
FR-FA-016 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Permission matrix enforcement | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-017 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Dealer portal role isolation | 36 | Security & Compliance | Separate internal workflow data from dealer visibility | MAPPED
FR-FA-018 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Executive read-only access | 15 | Identity & Access | Enforce record-scope hierarchical filtering | MAPPED
FR-FA-019 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Field-level visibility | 17 | Security & Compliance | Protect sensitive financial data at the field level | MAPPED
FR-FA-020 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Custom permission overrides | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-021 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Permission audit report | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-022 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Role change audit | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-023 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Temporary elevated access | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-024 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | API key management | 17 | Security & Compliance | Protect sensitive financial data at the field level | MAPPED
FR-FA-025 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Dealer portal user provisioning | 36 | Security & Compliance | Separate internal workflow data from dealer visibility | MAPPED
FR-FA-026 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Affinity group management | 22 | Reference Data Administration | Govern operational master data | MAPPED
FR-FA-027 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Ownership group management |  | Governance Data | Prepare authoritative master data | DEFERRED_SCOPE
FR-FA-028 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Product category management |  | Reference Data Administration | Govern operational master data | DEFERRED_SCOPE
FR-FA-029 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Brand label management |  | Reference Data Administration | Govern operational master data | DEFERRED_SCOPE
FR-FA-030 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Activity type management |  | Reference Data Administration | Govern operational master data | DEFERRED_SCOPE
FR-FA-031 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Industry classification management |  | Governance Data Management | Control reference-data changes safely | DEFERRED_SCOPE
FR-FA-032 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Company type management |  | Governance Data Management | Control reference-data changes safely | DEFERRED_SCOPE
FR-FA-033 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Distribution center management |  | Governance Data Management | Control reference-data changes safely | DEFERRED_SCOPE
FR-FA-034 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Training type management |  | Reference Data Administration | Govern operational master data | DEFERRED_SCOPE
FR-FA-035 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Reference data import/export |  | Governance Data Management | Control reference-data changes safely | DEFERRED_SCOPE
FR-FA-036 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Reference data change history |  | Governance Data Management | Control reference-data changes safely | DEFERRED_SCOPE
FR-FA-037 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Routing rule configuration |  | Admin Experience | Expose governed business controls | DEFERRED_SCOPE
FR-FA-038 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | SLA threshold configuration |  | Admin Experience | Expose governed business controls | DEFERRED_SCOPE
FR-FA-039 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Price class management |  | Reference Data Administration | Govern operational master data | DEFERRED_SCOPE
FR-FA-040 | FOUNDATION_SECURITY_ADMIN_PRD.md | Master Data, Admin Settings & Configuration | Dealer group rule management |  | Reference Data Administration | Govern operational master data | DEFERRED_SCOPE
FR-FA-041 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | User list | 36 | Security & Compliance | Separate internal workflow data from dealer visibility | MAPPED
FR-FA-042 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Create internal user | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-043 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Create dealer portal user | 36 | Security & Compliance | Separate internal workflow data from dealer visibility | MAPPED
FR-FA-044 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Deactivate user | 9 | Environments & Delivery | Operate reliable delivery environments | MODULE_MAPPED
FR-FA-045 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Territory assignment for user | 15 | Identity & Access | Enforce record-scope hierarchical filtering | MAPPED
FR-FA-046 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | User profile | 13 | Identity & Access | Secure internal and dealer access | MODULE_MAPPED
FR-FA-047 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Bulk user import | 13 | Identity & Access | Secure internal and dealer access | MODULE_MAPPED
FR-FA-048 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Last login tracking | 15 | Identity & Access | Enforce record-scope hierarchical filtering | MODULE_MAPPED
FR-FA-049 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | User search | 14 | Identity & Access | Enforce role-based permissions | MODULE_MAPPED
FR-FA-050 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Welcome email on user creation | 9 | Environments & Delivery | Operate reliable delivery environments | MODULE_MAPPED
FR-FA-051 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Audit log for all mutations | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-052 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Audit log viewer | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-053 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Login audit trail | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-054 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Audit log retention | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-055 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Audit log immutability | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-056 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Sensitive field audit | 17 | Security & Compliance | Protect sensitive financial data at the field level | MAPPED
FR-FA-057 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Export audit logs | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-058 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Failed action logging | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-059 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Environment separation | 12 | Environments & Delivery | Establish CI/CD pipeline and deployment runbook | MAPPED
FR-FA-060 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Feature flags | 18 | Release Controls | Control rollout safely by cohort and feature | MAPPED
FR-FA-061 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Feature flag by role | 18 | Release Controls | Control rollout safely by cohort and feature | MAPPED
FR-FA-062 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | System health dashboard | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-063 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Maintenance mode | 13 | Identity & Access | Secure internal and dealer access | MODULE_MAPPED
FR-FA-064 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Data export utility | 16 | Security & Compliance | Protect sensitive credit and personal data | MAPPED
FR-FA-065 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | System settings |  | Resilience & Trust | Manage database growth for high-volume tables | DEFERRED_SCOPE
FR-FA-066 | FOUNDATION_SECURITY_ADMIN_PRD.md | Program Foundation & Solution Architecture | Delegated admin authority | 4 | Solution Architecture | Define system boundaries | MAPPED
FR-FA-067 | FOUNDATION_SECURITY_ADMIN_PRD.md | Program Foundation & Solution Architecture | Single operational owner per account | 5 | Solution Architecture | Define canonical data model | MAPPED
FR-FA-068 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Read-only support role | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-069 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Geo/environment access controls | 13 | Identity & Access | Secure internal and dealer access | MAPPED
FR-FA-070 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Role plus label-based entitlements | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-071 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Immutable activity authorship | 19 | Observability & Audit | Create operational traceability | MAPPED
FR-FA-072 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Hosted sensitive-payment capture | 17 | Security & Compliance | Protect sensitive financial data at the field level | MAPPED
FR-FA-073 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Authenticated knowledge access | 14 | Identity & Access | Enforce role-based permissions | MAPPED
FR-FA-074 | FOUNDATION_SECURITY_ADMIN_PRD.md | Security, Identity, Environments & DevOps | Downstream sandbox dependency gate | 9 | Environments & Delivery | Operate reliable delivery environments | MAPPED
FR-LC-001 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Web form intake from 16+ Pulse branded sites | 40 | Lead Capture Replacement | Replace HubSpot and manual intake | MAPPED
FR-LC-002 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Source attribution auto-tagging | 41 | Lead Capture Replacement | Replace HubSpot and manual intake | MAPPED
FR-LC-003 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Manual lead entry form | 42 | Lead Intake Operations | Enable all inbound channels | MAPPED
FR-LC-004 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | CSV bulk import |  | Lead Intake Operations | Support bulk onboarding | DEFERRED_SCOPE
FR-LC-005 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Trade show lead capture | 46 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-006 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Affinity group roster import | 70 | Lead Operations | Enforce SLA and routing discipline | MAPPED
FR-LC-007 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Duplicate detection on create | 43 | Lead Intake Operations | Enable all inbound channels | MAPPED
FR-LC-008 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Duplicate detection on import | 70 | Lead Operations | Enforce SLA and routing discipline | MAPPED
FR-LC-009 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead identity validation | 42 | Lead Intake Operations | Enable all inbound channels | MAPPED
FR-LC-010 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | HubSpot migration import | 70 | Lead Operations | Enforce SLA and routing discipline | MAPPED
FR-LC-011 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Branded web form builder |  | Lead Capture Replacement | Replace HubSpot and manual intake | DEFERRED_SCOPE
FR-LC-012 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | API intake endpoint | 41 | Lead Capture Replacement | Replace HubSpot and manual intake | MAPPED
FR-LC-013 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Truck count routing | 47 | Lead Routing | Assign leads accurately and quickly | MAPPED
FR-LC-014 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Geography-based TM assignment | 72 | Lead Routing | Assign leads accurately and quickly | MAPPED
FR-LC-015 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Strategic Growth Team assignment | 47 | Lead Routing | Assign leads accurately and quickly | MAPPED
FR-LC-016 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Admin-configurable routing rules |  | Lead Capture Replacement | Replace HubSpot and manual intake | DEFERRED_SCOPE
FR-LC-017 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Manual routing override |  | Lead Capture Replacement | Replace HubSpot and manual intake | DEFERRED_SCOPE
FR-LC-018 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Round-robin within SGT |  | Lead Visibility | Give teams instant awareness | DEFERRED_SCOPE
FR-LC-019 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Affinity group routing influence | 70 | Lead Operations | Enforce SLA and routing discipline | MAPPED
FR-LC-020 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Routing audit trail | 69 | Lead Operations | Enforce SLA and routing discipline | MAPPED
FR-LC-021 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Seven-stage pipeline | 45 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-022 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Kanban pipeline view |  | Lead Lifecycle Management | Support complete pipeline lifecycle | DEFERRED_SCOPE
FR-LC-023 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Stage transition rules | 42 | Lead Intake Operations | Enable all inbound channels | MAPPED
FR-LC-024 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead detail view | 45 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-025 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Activity logging |  | Lead Routing | Notify both parties on lead ownership transfer | DEFERRED_SCOPE
FR-LC-026 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead rating | 48 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-027 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Discovery workflow |  | Lead Lifecycle Management | Support complete pipeline lifecycle | DEFERRED_SCOPE
FR-LC-028 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Discovery skip/fast-track | 48 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-029 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead search and filter | 43 | Lead Intake Operations | Enable all inbound channels | MAPPED
FR-LC-030 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead list view | 48 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-031 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead conversion to customer | 137 | Lead Conversion | Turn qualified prospects into customers | MAPPED
FR-LC-032 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead remains lead until first order | 137 | Lead Conversion | Turn qualified prospects into customers | MAPPED
FR-LC-033 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Dead lead handling | 48 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-034 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Lead reactivation |  | Lead Routing | Notify both parties on lead ownership transfer | DEFERRED_SCOPE
FR-LC-035 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Potential value tracking | 45 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-036 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Initial contact SLA | 69 | Lead Operations | Enforce SLA and routing discipline | MAPPED
FR-LC-037 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | SLA visual indicators | 71 | Lead Response | Enforce response accountability | MAPPED
FR-LC-038 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | SLA breach alert | 69 | Lead Operations | Enforce SLA and routing discipline | MAPPED
FR-LC-039 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Escalation chain | 71 | Lead Response | Enforce response accountability | MAPPED
FR-LC-040 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Admin-configurable SLA thresholds |  | Lead Capture Replacement | Replace HubSpot and manual intake | DEFERRED_SCOPE
FR-LC-041 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | SLA dashboard | 71 | Lead Response | Enforce response accountability | MAPPED
FR-LC-042 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Stage aging tracking | 42 | Lead Intake Operations | Enable all inbound channels | MAPPED
FR-LC-043 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Mobile lead list | 48 | Lead Operations | Run the full lead lifecycle | MAPPED
FR-LC-044 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Mobile lead detail | 40 | Lead Capture Replacement | Replace HubSpot and manual intake | MAPPED
FR-LC-045 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Mobile activity logging |  | Lead Routing | Notify both parties on lead ownership transfer | DEFERRED_SCOPE
FR-LC-046 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead Capture & Lead Management | Mobile business card OCR |  | Lead Intake Operations | Support bulk onboarding | DEFERRED_SCOPE
FR-PR-001 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | ERP-aligned price class master | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-002 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price class CRUD | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-003 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Customer price class assignment |  | Price Outputs | Produce usable sales artifacts | DEFERRED_SCOPE
FR-PR-004 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Dealer group → price class mapping | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-005 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price class override | 147 | Pricing Governance | Preserve price history and override accountability | MAPPED
FR-PR-006 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price class history | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-007 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Dual currency support |  | Currency & Tax | Handle cross-border B2B rules | DEFERRED_SCOPE
FR-PR-008 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Currency assignment |  | Currency & Tax | Handle cross-border B2B rules | DEFERRED_SCOPE
FR-PR-009 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price visibility by role | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-010 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price class admin dashboard | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-011 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price book sync |  | Dealer Publish | Push pricing to the portal | DEFERRED_SCOPE
FR-PR-012 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Sync frequency |  | Dealer Publish | Push pricing to the portal | DEFERRED_SCOPE
FR-PR-013 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price entry fields |  | Pricing Operations | Support large-scale price changes | DEFERRED_SCOPE
FR-PR-014 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Sync audit trail | 147 | Pricing Governance | Preserve price history and override accountability | MAPPED
FR-PR-015 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Sync error handling |  | Dealer Publish | Push pricing to the portal | DEFERRED_SCOPE
FR-PR-016 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price change detection | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-017 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price effective dating |  | Pricing Operations | Support large-scale price changes | DEFERRED_SCOPE
FR-PR-018 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price publish control | 147 | Pricing Governance | Preserve price history and override accountability | MAPPED
FR-PR-019 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price sheet generation |  | Price Outputs | Produce usable sales artifacts | DEFERRED_SCOPE
FR-PR-020 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price book comparison | 147 | Pricing Governance | Preserve price history and override accountability | MAPPED
FR-PR-021 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Portal login price resolution | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-022 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Catalog price display | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-023 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Cart price resolution | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-024 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Checkout price lock | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-025 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Credit hold impact | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-026 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Price not found handling | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-027 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Volume pricing (future) | 99 | Pricing Governance | Govern commercial pricing inputs | MAPPED
FR-PR-028 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Promotional pricing (future) |  | Pricing Governance | Govern commercial pricing inputs | DEFERRED_SCOPE
FR-PR-029 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Wildcard pricing support |  | Pricing Governance | Govern commercial pricing inputs | DEFERRED_SCOPE
FR-PR-030 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Portal price is pre-invoice price | 99 | Pricing Governance | Govern commercial pricing inputs | MAPPED
FR-PR-031 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | ERP invoice pushback | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-032 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Credit-hold order behavior | 146 | Checkout Resolution | Handle pricing exceptions safely at the point of order | MAPPED
FR-PR-033 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Manual/controlled publish cadence |  | Dealer Publish | Push pricing to the portal | DEFERRED_SCOPE
FR-PR-034 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Rebate boundary |  | Boundary Decisions | Keep complex pricing scope under control | DEFERRED_SCOPE
FR-PR-035 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | Multi-currency portal separation | 99 | Pricing Governance | Govern commercial pricing inputs | MAPPED
FR-PR-036 | PRICING_COMMERCIAL_RULES_PRD.md | Pricing & ERP-Dependent Commercial Rules | No stock-gating dependency for order capture |  | Freight Estimation | Guide shipping expectations | DEFERRED_SCOPE
FR-TR-001 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Hierarchy model |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-002 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Territory CRUD |  | Transfer Workflow | Manage territory changes cleanly | DEFERRED_SCOPE
FR-TR-003 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Region CRUD |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-004 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | TM assignment | 66 | Territory Model | Define and maintain territory ownership | MAPPED
FR-TR-005 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | RD assignment | 66 | Territory Model | Define and maintain territory ownership | MAPPED
FR-TR-006 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Customer-to-territory assignment | 65 | Routing Integration | Use territory logic in lead assignment | MAPPED
FR-TR-007 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Multi-territory customer | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-008 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Territory transfer |  | Transfer Workflow | Manage territory changes cleanly | DEFERRED_SCOPE
FR-TR-009 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Bulk territory operations |  | Territory Operations | Support operational territory changes | DEFERRED_SCOPE
FR-TR-010 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Organization chart view |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-011 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Interactive territory map | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-012 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Customer pins on map | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-013 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Pin click → customer detail | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-014 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Map filters | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-015 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Heat map layer | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-016 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | White space analysis |  | Territory Analytics | Let leaders inspect coverage and performance | DEFERRED_SCOPE
FR-TR-017 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Territory boundary editing |  | Boundary Management | Support controlled changes to the map | DEFERRED_SCOPE
FR-TR-018 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Map legend |  | Territory Model | Manage residential territories visually | DEFERRED_SCOPE
FR-TR-019 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Distribution center overlay |  | Strategic Growth | Support overlapping pursuit teams | DEFERRED_SCOPE
FR-TR-020 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Export map as image | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-021 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Route creation |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-022 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Route optimization |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-023 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Route map view |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-024 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Check-in/check-out |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-025 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Visit logging |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-026 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Route history |  | Transfer Workflow | Manage territory changes cleanly | DEFERRED_SCOPE
FR-TR-027 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Route suggestions |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-028 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Driving directions |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-029 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Territory performance dashboard |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-030 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | RD rollup dashboard |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-031 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | TM activity metrics |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-032 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Territory revenue trending |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-033 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Customer coverage score | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-034 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Peer comparison | 37 | Territory Model | Manage residential territories visually | MODULE_MAPPED
FR-TR-035 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Territory health score |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-036 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Pipeline by territory | 31 | Territory Foundation | Establish minimal ownership kernel | MAPPED
FR-TR-037 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Overlap detection | 65 | Routing Integration | Use territory logic in lead assignment | MAPPED
FR-TR-038 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Territory comparison report | 37 | Territory Model | Manage residential territories visually | MAPPED
FR-TR-039 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Mixed-stop route planning |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-040 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Configurable stop duration |  | Territory Analytics | Measure territory performance and engagement | DEFERRED_SCOPE
FR-TR-041 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Schedule-first workflow |  | Territory Operations | Support operational territory changes | DEFERRED_SCOPE
FR-TR-042 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Linked schedule completion | 31 | Territory Foundation | Establish minimal ownership kernel | MAPPED
FR-TR-043 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Role-filtered territory views | 64 | Access Views | Tailor territory insight by role | MAPPED
FR-TR-044 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | External navigation handoff |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-045 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Training-aware route suggestions |  | Mapping Controls | Make field routing predictable across regions | DEFERRED_SCOPE
FR-TR-046 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Primary-owner with overlay support |  | Strategic Growth | Support overlapping pursuit teams | DEFERRED_SCOPE
FR-TR-047 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Reassignment history preservation |  | Territory Operations | Support operational territory changes | DEFERRED_SCOPE
FR-TR-048 | TERRITORY_MANAGEMENT_PRD.md | Territory Management & Field Routing | Office-side assignment map usage |  | Boundary Management | Support controlled changes to the map | DEFERRED_SCOPE
FR-TM-001 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training type enumeration | 101 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-002 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training templates | 150 | Training Proof | Turn training into executive proof | MAPPED
FR-TM-003 | TRAINING_MANAGEMENT_PRD.md | Training Management | Onboarding training auto-creation |  | Onboarding Curriculum | Standardize early customer education | DEFERRED_SCOPE
FR-TM-004 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training categories |  | Training Catalog | Standardize what training can be delivered | DEFERRED_SCOPE
FR-TM-005 | TRAINING_MANAGEMENT_PRD.md | Training Management | Mandatory training requirements | 101 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-006 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training resource library |  | Training Catalog | Standardize what training can be delivered | DEFERRED_SCOPE
FR-TM-007 | TRAINING_MANAGEMENT_PRD.md | Training Management | Cadence rules |  | Training Compliance | Automate compliance tracking and alerts | DEFERRED_SCOPE
FR-TM-008 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training compliance checker |  | Training Compliance | Automate compliance tracking and alerts | DEFERRED_SCOPE
FR-TM-009 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training recommendation engine | 151 | Training Proof | Turn training into executive proof | MAPPED
FR-TM-010 | TRAINING_MANAGEMENT_PRD.md | Training Management | Trainer management | 151 | Training Proof | Turn training into executive proof | MAPPED
FR-TM-011 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training session creation | 151 | Training Proof | Turn training into executive proof | MAPPED
FR-TM-012 | TRAINING_MANAGEMENT_PRD.md | Training Management | Outlook 365 calendar sync |  | Calendar Sync | Keep CRM and Outlook aligned | DEFERRED_SCOPE
FR-TM-013 | TRAINING_MANAGEMENT_PRD.md | Training Management | Outlook event structure |  | Calendar Sync | Keep CRM and Outlook aligned | DEFERRED_SCOPE
FR-TM-014 | TRAINING_MANAGEMENT_PRD.md | Training Management | Bidirectional sync behavior |  | Calendar Sync | Keep CRM and Outlook aligned | DEFERRED_SCOPE
FR-TM-015 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training calendar view | 103 | Training Scheduling | Manage training commitments from CRM | MAPPED
FR-TM-016 | TRAINING_MANAGEMENT_PRD.md | Training Management | Scheduling conflict detection |  | Scheduling Governance | Coordinate training at scale without manual cleanup | DEFERRED_SCOPE
FR-TM-017 | TRAINING_MANAGEMENT_PRD.md | Training Management | Bulk scheduling |  | Scheduling Governance | Coordinate training at scale without manual cleanup | DEFERRED_SCOPE
FR-TM-018 | TRAINING_MANAGEMENT_PRD.md | Training Management | Reschedule workflow |  | Calendar Sync | Keep CRM and Outlook aligned | DEFERRED_SCOPE
FR-TM-019 | TRAINING_MANAGEMENT_PRD.md | Training Management | Cancellation workflow |  | Training Catalog | Standardize what training can be delivered | DEFERRED_SCOPE
FR-TM-020 | TRAINING_MANAGEMENT_PRD.md | Training Management | Recurring training setup |  | Scheduling Governance | Coordinate training at scale without manual cleanup | DEFERRED_SCOPE
FR-TM-021 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training session status |  | Training Catalog | Standardize what training can be delivered | DEFERRED_SCOPE
FR-TM-022 | TRAINING_MANAGEMENT_PRD.md | Training Management | Attendance tracking | 100 | Completion Tracking | Prove what was delivered | MAPPED
FR-TM-023 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training outcome | 100 | Completion Tracking | Prove what was delivered | MAPPED
FR-TM-024 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training notes |  | Training Catalog | Standardize what training can be delivered | DEFERRED_SCOPE
FR-TM-025 | TRAINING_MANAGEMENT_PRD.md | Training Management | Proof of training | 101 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-026 | TRAINING_MANAGEMENT_PRD.md | Training Management | Photo proof capture (mobile) | 101 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-027 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training feedback survey |  | Certification Lifecycle | Capture proof and follow-up from training events | DEFERRED_SCOPE
FR-TM-028 | TRAINING_MANAGEMENT_PRD.md | Training Management | Follow-up task generation | 100 | Completion Tracking | Prove what was delivered | MAPPED
FR-TM-029 | TRAINING_MANAGEMENT_PRD.md | Training Management | Training effectiveness score |  | Certification Lifecycle | Capture proof and follow-up from training events | DEFERRED_SCOPE
FR-TM-030 | TRAINING_MANAGEMENT_PRD.md | Training Management | Incentive/contest tracking |  | Training Analytics | Measure the impact of training investments | DEFERRED_SCOPE
FR-TM-031 | TRAINING_MANAGEMENT_PRD.md | Training Management | Certification programs |  | Certification Integration | Connect learning credentials | DEFERRED_SCOPE
FR-TM-032 | TRAINING_MANAGEMENT_PRD.md | Training Management | Certification lifecycle |  | Certification Lifecycle | Capture proof and follow-up from training events | DEFERRED_SCOPE
FR-TM-033 | TRAINING_MANAGEMENT_PRD.md | Training Management | Auto-certification |  | Certification Integration | Connect learning credentials | DEFERRED_SCOPE
FR-TM-034 | TRAINING_MANAGEMENT_PRD.md | Training Management | Expiration alerts |  | Training Compliance | Automate compliance tracking and alerts | DEFERRED_SCOPE
FR-TM-035 | TRAINING_MANAGEMENT_PRD.md | Training Management | Certification dashboard |  | Certification Integration | Connect learning credentials | DEFERRED_SCOPE
FR-TM-036 | TRAINING_MANAGEMENT_PRD.md | Training Management | Recertification workflow | 100 | Completion Tracking | Prove what was delivered | MAPPED
FR-TM-037 | TRAINING_MANAGEMENT_PRD.md | Training Management | Certificate generation | 151 | Training Proof | Turn training into executive proof | MAPPED
FR-TM-038 | TRAINING_MANAGEMENT_PRD.md | Training Management | IAQ Certification Prep tracking |  | Training Compliance | Automate compliance tracking and alerts | DEFERRED_SCOPE
FR-TM-039 | TRAINING_MANAGEMENT_PRD.md | Training Management | Admin-managed training catalog |  | Training Catalog | Standardize what training can be delivered | DEFERRED_SCOPE
FR-TM-040 | TRAINING_MANAGEMENT_PRD.md | Training Management | Custom presentation option |  | Training Engagement | Track contests and custom content | DEFERRED_SCOPE
FR-TM-041 | TRAINING_MANAGEMENT_PRD.md | Training Management | Default cadence and exception reporting | 102 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-042 | TRAINING_MANAGEMENT_PRD.md | Training Management | Pulse-first scheduling |  | Scheduling Governance | Coordinate training at scale without manual cleanup | DEFERRED_SCOPE
FR-TM-043 | TRAINING_MANAGEMENT_PRD.md | Training Management | Minimal completion evidence | 100 | Completion Tracking | Prove what was delivered | MAPPED
FR-TM-044 | TRAINING_MANAGEMENT_PRD.md | Training Management | Contest and giveaway linkage |  | Training Analytics | Measure the impact of training investments | DEFERRED_SCOPE
FR-TM-045 | TRAINING_MANAGEMENT_PRD.md | Training Management | External training site coexistence | 102 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-046 | TRAINING_MANAGEMENT_PRD.md | Training Management | Technician attendee capture | 101 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-047 | TRAINING_MANAGEMENT_PRD.md | Training Management | Structured mobile training event capture | 101 | Training Record Operations | Track activity and proof at the customer level | MAPPED
FR-TM-048 | TRAINING_MANAGEMENT_PRD.md | Training Management | Role-based training KPI views | 103 | Training Scheduling | Manage training commitments from CRM | MAPPED
FR-TM-049 | TRAINING_MANAGEMENT_PRD.md | Training Management | Customer-centric training context |  | Training Proof | Turn training into executive proof | DEFERRED_SCOPE

## Scope Gaps & Unmapped FRs
Scope Gaps & Unmapped FRs
ID | Source | Title / Requirement | Module | Gap Type | Action Required
FR-AN-006 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Consignment Audit Due | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-007 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Consignment Audit Overdue | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-008 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | PO Clock Warning | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-009 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Training Reminder | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-010 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Customer At-Risk | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-012 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Training No-Show | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-014 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Sync Error | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-016 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Onboarding Step Complete | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-024 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Order Submitted | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-027 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Notification mark as read | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-028 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Email notifications | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-035 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Notification audit trail | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-039 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Template management | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-040 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Unified communication view | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-041 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication search | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-043 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Communication metrics | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-044 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Email context linking | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-045 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Training inactivity red flag | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-046 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Consignment operational alerts | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-048 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Touchpoint completeness | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-049 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Territory-aware recipients | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-051 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Order-activity monitoring baseline | Communication, Notifications & Alerts | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CIS-001 | CIS_CREDIT_ONBOARDING_PRD.md | Generate unique CIS link | CIS, Credit & Onboarding Workflow | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CIS-012 | CIS_CREDIT_ONBOARDING_PRD.md | CIS status tracking | CIS, Credit & Onboarding Workflow | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CIS-014 | CIS_CREDIT_ONBOARDING_PRD.md | CIS expiration | CIS, Credit & Onboarding Workflow | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CIS-030 | CIS_CREDIT_ONBOARDING_PRD.md | 3 WebEx training sessions | CIS, Credit & Onboarding Workflow | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CIS-031 | CIS_CREDIT_ONBOARDING_PRD.md | Training scheduling | CIS, Credit & Onboarding Workflow | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CIS-032 | CIS_CREDIT_ONBOARDING_PRD.md | Training completion tracking | CIS, Credit & Onboarding Workflow | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-007 | CONSIGNMENT_MANAGEMENT_PRD.md | BLUE form workflow | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-008 | CONSIGNMENT_MANAGEMENT_PRD.md | Disenrollment workflow | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-022 | CONSIGNMENT_MANAGEMENT_PRD.md | Barcode scanning (mobile) | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-023 | CONSIGNMENT_MANAGEMENT_PRD.md | Audit photos | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-028 | CONSIGNMENT_MANAGEMENT_PRD.md | Discrepancy resolution workflow | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-029 | CONSIGNMENT_MANAGEMENT_PRD.md | PO follow-up — 5 business day clock | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-030 | CONSIGNMENT_MANAGEMENT_PRD.md | PO clock alerts | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-031 | CONSIGNMENT_MANAGEMENT_PRD.md | PO received confirmation | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-032 | CONSIGNMENT_MANAGEMENT_PRD.md | PO overdue escalation | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-033 | CONSIGNMENT_MANAGEMENT_PRD.md | Inventory baseline update | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-034 | CONSIGNMENT_MANAGEMENT_PRD.md | Acumatica inventory sync | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-036 | CONSIGNMENT_MANAGEMENT_PRD.md | BLUE cycle | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-037 | CONSIGNMENT_MANAGEMENT_PRD.md | PURPLE cycle | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-038 | CONSIGNMENT_MANAGEMENT_PRD.md | SAND cycle | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-039 | CONSIGNMENT_MANAGEMENT_PRD.md | Cycle type tracking | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-040 | CONSIGNMENT_MANAGEMENT_PRD.md | Cycle scheduling rules | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-048 | CONSIGNMENT_MANAGEMENT_PRD.md | Variance drilldown | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-049 | CONSIGNMENT_MANAGEMENT_PRD.md | Manual count remains required | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-050 | CONSIGNMENT_MANAGEMENT_PRD.md | Customer account indicator | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-052 | CONSIGNMENT_MANAGEMENT_PRD.md | BLUE/PURPLE document semantics | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CSG-054 | CONSIGNMENT_MANAGEMENT_PRD.md | Formal exit workflow controls | Consignment Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-015 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Customer merge | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-019 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Contact-to-portal user link | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-034 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Dealer group resolution algorithm | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-037 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Dealer group override | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-038 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Price class history | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-042 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Invoices tab | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-043 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Shipments tab | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-044 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Payments tab | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-CA-046 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Read-only financial data | Customer, Account, Contact & Multi-Location Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-002 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset metadata | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-004 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset search | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-006 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset download | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-008 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Folder organization | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-009 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset sharing | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-010 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset usage tracking | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-014 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Storage quota monitoring | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-015 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset archive/delete | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-019 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Brand label scoping | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-023 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Dealer-safe downloads | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-024 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Downloads page | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-025 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Branded export packs | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-026 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset access audit | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-027 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Curated collections | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-028 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Mobile asset access | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-031 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Widen import tool | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-035 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Portal-style collections | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-036 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Quick search and send | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-037 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Better-than-folder UX | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-038 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Mobile-friendly asset access | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-039 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Internal admin app plus external portal split | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-040 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Asset-type filtering baseline | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-DA-041 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Mandatory ingest metadata validation | Digital Assets & Document Handling | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-004 | FOUNDATION_SECURITY_ADMIN_PRD.md | Session management | Security, Identity, Environments & DevOps | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-027 | FOUNDATION_SECURITY_ADMIN_PRD.md | Ownership group management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-028 | FOUNDATION_SECURITY_ADMIN_PRD.md | Product category management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-029 | FOUNDATION_SECURITY_ADMIN_PRD.md | Brand label management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-030 | FOUNDATION_SECURITY_ADMIN_PRD.md | Activity type management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-031 | FOUNDATION_SECURITY_ADMIN_PRD.md | Industry classification management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-032 | FOUNDATION_SECURITY_ADMIN_PRD.md | Company type management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-033 | FOUNDATION_SECURITY_ADMIN_PRD.md | Distribution center management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-034 | FOUNDATION_SECURITY_ADMIN_PRD.md | Training type management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-035 | FOUNDATION_SECURITY_ADMIN_PRD.md | Reference data import/export | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-036 | FOUNDATION_SECURITY_ADMIN_PRD.md | Reference data change history | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-037 | FOUNDATION_SECURITY_ADMIN_PRD.md | Routing rule configuration | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-038 | FOUNDATION_SECURITY_ADMIN_PRD.md | SLA threshold configuration | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-039 | FOUNDATION_SECURITY_ADMIN_PRD.md | Price class management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-040 | FOUNDATION_SECURITY_ADMIN_PRD.md | Dealer group rule management | Master Data, Admin Settings & Configuration | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-FA-065 | FOUNDATION_SECURITY_ADMIN_PRD.md | System settings | Security, Identity, Environments & DevOps | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-004 | LEAD_CAPTURE_MANAGEMENT_PRD.md | CSV bulk import | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-011 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Branded web form builder | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-016 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Admin-configurable routing rules | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-017 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Manual routing override | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-018 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Round-robin within SGT | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-022 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Kanban pipeline view | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-025 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Activity logging | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-027 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Discovery workflow | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-034 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Lead reactivation | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-040 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Admin-configurable SLA thresholds | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-045 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Mobile activity logging | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-LC-046 | LEAD_CAPTURE_MANAGEMENT_PRD.md | Mobile business card OCR | Lead Capture & Lead Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-003 | PRICING_COMMERCIAL_RULES_PRD.md | Customer price class assignment | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-007 | PRICING_COMMERCIAL_RULES_PRD.md | Dual currency support | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-008 | PRICING_COMMERCIAL_RULES_PRD.md | Currency assignment | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-011 | PRICING_COMMERCIAL_RULES_PRD.md | Price book sync | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-012 | PRICING_COMMERCIAL_RULES_PRD.md | Sync frequency | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-013 | PRICING_COMMERCIAL_RULES_PRD.md | Price entry fields | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-015 | PRICING_COMMERCIAL_RULES_PRD.md | Sync error handling | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-017 | PRICING_COMMERCIAL_RULES_PRD.md | Price effective dating | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-019 | PRICING_COMMERCIAL_RULES_PRD.md | Price sheet generation | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-028 | PRICING_COMMERCIAL_RULES_PRD.md | Promotional pricing (future) | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-029 | PRICING_COMMERCIAL_RULES_PRD.md | Wildcard pricing support | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-033 | PRICING_COMMERCIAL_RULES_PRD.md | Manual/controlled publish cadence | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-034 | PRICING_COMMERCIAL_RULES_PRD.md | Rebate boundary | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-PR-036 | PRICING_COMMERCIAL_RULES_PRD.md | No stock-gating dependency for order capture | Pricing & ERP-Dependent Commercial Rules | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-001 | TERRITORY_MANAGEMENT_PRD.md | Hierarchy model | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-002 | TERRITORY_MANAGEMENT_PRD.md | Territory CRUD | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-003 | TERRITORY_MANAGEMENT_PRD.md | Region CRUD | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-008 | TERRITORY_MANAGEMENT_PRD.md | Territory transfer | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-009 | TERRITORY_MANAGEMENT_PRD.md | Bulk territory operations | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-010 | TERRITORY_MANAGEMENT_PRD.md | Organization chart view | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-016 | TERRITORY_MANAGEMENT_PRD.md | White space analysis | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-017 | TERRITORY_MANAGEMENT_PRD.md | Territory boundary editing | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-018 | TERRITORY_MANAGEMENT_PRD.md | Map legend | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-019 | TERRITORY_MANAGEMENT_PRD.md | Distribution center overlay | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-021 | TERRITORY_MANAGEMENT_PRD.md | Route creation | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-022 | TERRITORY_MANAGEMENT_PRD.md | Route optimization | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-023 | TERRITORY_MANAGEMENT_PRD.md | Route map view | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-024 | TERRITORY_MANAGEMENT_PRD.md | Check-in/check-out | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-025 | TERRITORY_MANAGEMENT_PRD.md | Visit logging | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-026 | TERRITORY_MANAGEMENT_PRD.md | Route history | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-027 | TERRITORY_MANAGEMENT_PRD.md | Route suggestions | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-028 | TERRITORY_MANAGEMENT_PRD.md | Driving directions | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-029 | TERRITORY_MANAGEMENT_PRD.md | Territory performance dashboard | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-030 | TERRITORY_MANAGEMENT_PRD.md | RD rollup dashboard | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-031 | TERRITORY_MANAGEMENT_PRD.md | TM activity metrics | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-032 | TERRITORY_MANAGEMENT_PRD.md | Territory revenue trending | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-035 | TERRITORY_MANAGEMENT_PRD.md | Territory health score | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-039 | TERRITORY_MANAGEMENT_PRD.md | Mixed-stop route planning | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-040 | TERRITORY_MANAGEMENT_PRD.md | Configurable stop duration | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-041 | TERRITORY_MANAGEMENT_PRD.md | Schedule-first workflow | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-044 | TERRITORY_MANAGEMENT_PRD.md | External navigation handoff | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-045 | TERRITORY_MANAGEMENT_PRD.md | Training-aware route suggestions | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-046 | TERRITORY_MANAGEMENT_PRD.md | Primary-owner with overlay support | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-047 | TERRITORY_MANAGEMENT_PRD.md | Reassignment history preservation | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TR-048 | TERRITORY_MANAGEMENT_PRD.md | Office-side assignment map usage | Territory Management & Field Routing | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-003 | TRAINING_MANAGEMENT_PRD.md | Onboarding training auto-creation | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-004 | TRAINING_MANAGEMENT_PRD.md | Training categories | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-006 | TRAINING_MANAGEMENT_PRD.md | Training resource library | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-007 | TRAINING_MANAGEMENT_PRD.md | Cadence rules | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-008 | TRAINING_MANAGEMENT_PRD.md | Training compliance checker | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-012 | TRAINING_MANAGEMENT_PRD.md | Outlook 365 calendar sync | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-013 | TRAINING_MANAGEMENT_PRD.md | Outlook event structure | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-014 | TRAINING_MANAGEMENT_PRD.md | Bidirectional sync behavior | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-016 | TRAINING_MANAGEMENT_PRD.md | Scheduling conflict detection | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-017 | TRAINING_MANAGEMENT_PRD.md | Bulk scheduling | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-018 | TRAINING_MANAGEMENT_PRD.md | Reschedule workflow | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-019 | TRAINING_MANAGEMENT_PRD.md | Cancellation workflow | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-020 | TRAINING_MANAGEMENT_PRD.md | Recurring training setup | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-021 | TRAINING_MANAGEMENT_PRD.md | Training session status | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-024 | TRAINING_MANAGEMENT_PRD.md | Training notes | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-027 | TRAINING_MANAGEMENT_PRD.md | Training feedback survey | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-029 | TRAINING_MANAGEMENT_PRD.md | Training effectiveness score | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-030 | TRAINING_MANAGEMENT_PRD.md | Incentive/contest tracking | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-031 | TRAINING_MANAGEMENT_PRD.md | Certification programs | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-032 | TRAINING_MANAGEMENT_PRD.md | Certification lifecycle | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-033 | TRAINING_MANAGEMENT_PRD.md | Auto-certification | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-034 | TRAINING_MANAGEMENT_PRD.md | Expiration alerts | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-035 | TRAINING_MANAGEMENT_PRD.md | Certification dashboard | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-038 | TRAINING_MANAGEMENT_PRD.md | IAQ Certification Prep tracking | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-039 | TRAINING_MANAGEMENT_PRD.md | Admin-managed training catalog | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-040 | TRAINING_MANAGEMENT_PRD.md | Custom presentation option | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-042 | TRAINING_MANAGEMENT_PRD.md | Pulse-first scheduling | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-044 | TRAINING_MANAGEMENT_PRD.md | Contest and giveaway linkage | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-TM-049 | TRAINING_MANAGEMENT_PRD.md | Customer-centric training context | Training Management | Deferred in 1603-SP baseline | Carry in post-core backlog or later phase
FR-AN-003 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | CIS Submitted | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-AN-004 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | CIS Finance Submitted | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-AN-013 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Certification Expiring | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-AN-017 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Territory Reassignment | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-AN-018 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Report Ready | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-AN-019 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Discrepancy Case Created | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-AN-020 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | System Maintenance | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-AN-021 | ALERTS_NOTIFICATIONS_COMMUNICATION_PRD.md | Stage Transition | Communication, Notifications & Alerts | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-CIS-008 | CIS_CREDIT_ONBOARDING_PRD.md | Save as draft | CIS, Credit & Onboarding Workflow | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-CIS-029 | CIS_CREDIT_ONBOARDING_PRD.md | Welcome email | CIS, Credit & Onboarding Workflow | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-CSG-003 | CONSIGNMENT_MANAGEMENT_PRD.md | Agreement template | Consignment Management | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-CA-023 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Training attendance linking | Customer, Account, Contact & Multi-Location Management | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-CA-032 | CUSTOMER_ACCOUNT_CONTACT_PRD.md | Consignment site linking | Customer, Account, Contact & Multi-Location Management | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-DA-013 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Image optimization | Digital Assets & Document Handling | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-DA-032 | DIGITAL_ASSETS_DOCUMENTS_PRD.md | Duplicate detection | Digital Assets & Document Handling | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-003 | FOUNDATION_SECURITY_ADMIN_PRD.md | JWT token issuance | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-006 | FOUNDATION_SECURITY_ADMIN_PRD.md | Account lockout | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-010 | FOUNDATION_SECURITY_ADMIN_PRD.md | Session timeout | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-044 | FOUNDATION_SECURITY_ADMIN_PRD.md | Deactivate user | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-046 | FOUNDATION_SECURITY_ADMIN_PRD.md | User profile | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-047 | FOUNDATION_SECURITY_ADMIN_PRD.md | Bulk user import | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-048 | FOUNDATION_SECURITY_ADMIN_PRD.md | Last login tracking | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-049 | FOUNDATION_SECURITY_ADMIN_PRD.md | User search | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-050 | FOUNDATION_SECURITY_ADMIN_PRD.md | Welcome email on user creation | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-FA-063 | FOUNDATION_SECURITY_ADMIN_PRD.md | Maintenance mode | Security, Identity, Environments & DevOps | Module-level heuristic only | Review and replace with explicit row mapping if needed
FR-TR-034 | TERRITORY_MANAGEMENT_PRD.md | Peer comparison | Territory Management & Field Routing | Module-level heuristic only | Review and replace with explicit row mapping if needed

## Expanded WBS + FR Mapping
Expanded WBS + FR Mapping
WBS Row # | Module | Epic | Story | Task | Component | Dependencies | Story_Points | Sprint | Priority | Mapped_FR_Count | Sample_FR_IDs
2 | Program Foundation & Solution Architecture | Program Governance | Launch the target-state delivery program | Establish charter and success metrics | Program Office | None | 8 | Sprint 01 | P0 | 0
3 | Program Foundation & Solution Architecture | Program Governance | Launch the target-state delivery program | Define governance cadence and decision rights | Program Office | Charter and success metrics | 5 | Sprint 01 | P0 | 0
4 | Program Foundation & Solution Architecture | Solution Architecture | Define system boundaries | Set CRM, dealer portal, mobile, and Acumatica source-of-truth rules | Solution Architecture | Charter and success metrics | 8 | Sprint 01 | P0 | 1 | FR-FA-066
5 | Program Foundation & Solution Architecture | Solution Architecture | Define canonical data model | Model lead, account, contact, location, training, consignment, activity, and reporting entities | Data Architecture | Source-of-truth rules | 13 | Sprint 01 | P0 | 1 | FR-FA-067
6 | Program Foundation & Solution Architecture | Solution Architecture | Lock customer lifecycle boundary | Lock customer-creation trigger and downstream lifecycle definitions | Solution Architecture | Source-of-truth rules | 5 | Sprint 01 | P0 | 0
7 | Program Foundation & Solution Architecture | Experience Principles | Build adoption-first experience | Define web, mobile, and dealer UX standards | UX System Design | Governance cadence | 5 | Sprint 01 | P1 | 0
8 | Program Foundation & Solution Architecture | Experience Principles | Build reporting-first information architecture | Define KPI taxonomy, navigation, and naming conventions | Product Design | Canonical data model | 5 | Sprint 01 | P1 | 0
9 | Security, Identity, Environments & DevOps | Environments & Delivery | Operate reliable delivery environments | Provision dev, test, UAT, and production environments | Platform | Governance cadence | 8 | Sprint 01 | P0 | 5 | FR-FA-003, FR-FA-006, FR-FA-044, FR-FA-050, FR-FA-074
10 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 01 - Release Buffer | UAT, bug fixes, deployment, stabilization | Testing & Release | Seq 01 features complete | 5 | Sprint 01 | P0 | 0
11 | Program Foundation & Solution Architecture | Solution Architecture | Lock physical data baseline | Generate and approve physical schema, audit model, masking, and indexing baseline | Data Architecture | Canonical data model and boundary decisions | 8 | Sprint 02 | P0 | 0
12 | Security, Identity, Environments & DevOps | Environments & Delivery | Establish CI/CD pipeline and deployment runbook | Build CI/CD pipeline with environment promotion | Platform | Environment baseline | 13 | Sprint 02 | P0 | 1 | FR-FA-059
13 | Security, Identity, Environments & DevOps | Identity & Access | Secure internal and dealer access | Implement internal SSO and dealer identity patterns | Identity | Environment baseline | 8 | Sprint 02 | P0 | 6 | FR-FA-001, FR-FA-005, FR-FA-046, FR-FA-047, FR-FA-063
14 | Security, Identity, Environments & DevOps | Identity & Access | Enforce role-based permissions | Configure permission matrix for internal teams and dealer contacts | Access Control | Identity patterns | 8 | Sprint 02 | P0 | 15 | FR-FA-007, FR-FA-009, FR-FA-010, FR-FA-011, FR-FA-012
15 | Security, Identity, Environments & DevOps | Identity & Access | Enforce record-scope hierarchical filtering | Build own/team/subordinate/all record-scope filters | Access Control | Role-based permissions and minimal territory ownership matrix | 8 | Sprint 02 | P0 | 4 | FR-FA-013, FR-FA-018, FR-FA-045, FR-FA-048
16 | Security, Identity, Environments & DevOps | Security & Compliance | Protect sensitive credit and personal data | Segregate PCI data, tokenization, and redaction controls | Security | Source-of-truth rules | 13 | Sprint 02 | P0 | 1 | FR-FA-064
17 | Security, Identity, Environments & DevOps | Security & Compliance | Protect sensitive financial data at the field level | Implement field-level data masking for PCI-sensitive fields | Security | Identity patterns and PCI controls | 8 | Sprint 02 | P0 | 4 | FR-FA-019, FR-FA-024, FR-FA-056, FR-FA-072
18 | Security, Identity, Environments & DevOps | Release Controls | Control rollout safely by cohort and feature | Implement feature-flag and cohort-targeting framework | Feature Flags | Build CI/CD pipeline with environment promotion and Implement internal SSO and dealer identity patterns | 5 | Sprint 03 | P0 | 2 | FR-FA-060, FR-FA-061
19 | Security, Identity, Environments & DevOps | Observability & Audit | Create operational traceability | Implement audit logging, sync logs, and admin activity history | Monitoring | Role-based permissions | 8 | Sprint 03 | P1 | 11 | FR-FA-008, FR-FA-022, FR-FA-051, FR-FA-052, FR-FA-053
20 | Security, Identity, Environments & DevOps | Resilience & Trust | Prepare for secure operations | Configure backups, recovery runbooks, uptime monitoring, and AI guardrails | Platform Operations | Environment baseline | 5 | Sprint 03 | P1 | 0
21 | Master Data, Admin Settings & Configuration | Admin Experience | Give admins usable control surfaces | Build CRUD workflows with validation and audit history | Admin UI | Reference data loaded | 8 | Sprint 03 | P0 | 0
22 | Master Data, Admin Settings & Configuration | Reference Data Administration | Govern operational master data | Seed affinity groups and ownership groups from legacy reference exports | Admin Console | Canonical data model | 8 | Sprint 03 | P0 | 1 | FR-FA-026
23 | Master Data, Admin Settings & Configuration | Reference Data Administration | Govern operational master data | Import lead sources, customer classes, training categories, and capture settings | Lead Capture Admin | Brand config | 5 | Sprint 03 | P0 | 0
24 | Acumatica Integration & Data Migration | Integration Blueprint | Define the integration contract | Specify APIs, events, schedules, and ownership for customer, order, invoice, payment, shipment, pricing, and product data | Integration Design | Source-of-truth rules | 13 | Sprint 03 | P0 | 0
25 | Acumatica Integration & Data Migration | Integration Blueprint | Define the integration contract | Produce signed field-mapping workbooks for customer, contact, product, pricing, consignment, order, and reporting entities | Field Mapping | Source-of-truth rules and canonical data model | 13 | Sprint 03 | P0 | 0
26 | Acumatica Integration & Data Migration | Integration Blueprint | Prove integration environment readiness | Certify Acumatica sandbox access, auth, endpoint coverage, and queue-DLQ readiness | Integration Environment | Integration contract and field mappings | 8 | Sprint 04 | P0 | 0
27 | Acumatica Integration & Data Migration | Integration Governance | Keep consumers off unstable contracts | Define API versioning, compatibility, and deprecation policy | API Governance | Specify APIs, events, schedules, and ownership for customer, order, invoice, payment, shipment, pricing, and product data | 5 | Sprint 04 | P0 | 0
28 | Acumatica Integration & Data Migration | Integration Resilience | Prevent duplicate processing and replay errors | Implement idempotency-key and duplicate-event protection | Integration Resilience | Specify APIs, events, schedules, and ownership for customer, order, invoice, payment, shipment, pricing, and product data and Define API versioning, compatibility, and deprecation policy | 5 | Sprint 04 | P0 | 0
29 | Acumatica Integration & Data Migration | Integration Resilience | Recover safely from failed event handling | Build replay and reprocessing controls with poison-message quarantine | Replay Controls | Implement idempotency-key and duplicate-event protection and Certify Acumatica sandbox access, auth, endpoint coverage, and queue-DLQ readiness | 8 | Sprint 04 | P0 | 0
30 | Acumatica Integration & Data Migration | Migration Governance | Define migration go/no-go rules before build scales | Define migration acceptance thresholds and reconciliation tolerances by source stream | Migration Governance | Produce signed field-mapping workbooks for customer, contact, product, pricing, consignment, order, and reporting entities | 5 | Sprint 04 | P0 | 0
31 | Territory Management & Field Routing | Territory Foundation | Establish minimal ownership kernel | Seed minimal territory ownership matrix for routing and security scopes | Territory Seed Data | Reference data and role model | 5 | Sprint 04 | P0 | 2 | FR-TR-036, FR-TR-042
32 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 02 - Release Buffer | UAT, bug fixes, deployment, stabilization | Testing & Release | Seq 02 features complete | 13 | Sprint 04 | P0 | 0
33 | Mobile Field App | Mobile Foundation | Handle errors gracefully in the field | Build mobile error handling framework for 11 scenarios | Mobile App | Mobile foundation | 8 | Sprint 04 | P0 | 0
34 | Mobile Field App | Mobile Foundation | Deliver a field-ready mobile experience | Build the mobile shell, secure login, and profile management | Mobile App | Identity patterns | 8 | Sprint 04 | P0 | 0
35 | QA, UAT, Rollout & Adoption | Release & Stabilization | M-Seq 02 - Release Buffer | UAT, bug fixes, deployment, stabilization | Testing & Release | M-Seq 02 features complete | 5 | Sprint 05 | P0 | 0
36 | Security, Identity, Environments & DevOps | Security & Compliance | Separate internal workflow data from dealer visibility | Build internal notes and workflow status masking for dealer portal | Access Control | Dealer identity and role-based permissions | 5 | Sprint 05 | P0 | 6 | FR-FA-002, FR-FA-015, FR-FA-017, FR-FA-025, FR-FA-041
37 | Territory Management & Field Routing | Territory Model | Manage residential territories visually | Build an interactive map with states, territory ownership, and customer overlays | Territory Map | Customer geo data | 13 | Sprint 05 | P0 | 10 | FR-TR-007, FR-TR-011, FR-TR-012, FR-TR-013, FR-TR-014
38 | Communication, Notifications & Alerts | Alert Engine | Create one notification framework | Define rule-driven alerts, delivery channels, and acknowledgment states | Notification Engine | Access control and communication hub | 8 | Sprint 05 | P0 | 7 | FR-AN-003, FR-AN-004, FR-AN-013, FR-AN-018, FR-AN-020
39 | Communication, Notifications & Alerts | Alert Platform Readiness | Prove the alert engine before consumers scale | Certify shared alert engine readiness before downstream consumers | Alert Engine | Define rule-driven alerts, delivery channels, and acknowledgment states | 5 | Sprint 05 | P0 | 6 | FR-AN-019, FR-AN-021, FR-AN-025, FR-AN-031, FR-AN-033
40 | Lead Capture & Lead Management | Lead Capture Replacement | Replace HubSpot and manual intake | Publish embeddable branded lead forms | Web Widget | Lead capture admin | 8 | Sprint 05 | P0 | 2 | FR-LC-001, FR-LC-044
41 | Lead Capture & Lead Management | Lead Capture Replacement | Replace HubSpot and manual intake | Auto-tag source, brand, and campaign metadata | Lead Intake API | Branded lead forms | 5 | Sprint 05 | P0 | 2 | FR-LC-002, FR-LC-012
42 | Lead Capture & Lead Management | Lead Intake Operations | Enable all inbound channels | Support manual BD lead entry | Lead Intake | Lead stage and routing configuration | 5 | Sprint 05 | P0 | 4 | FR-LC-003, FR-LC-009, FR-LC-023, FR-LC-042
43 | Lead Capture & Lead Management | Lead Intake Operations | Enable all inbound channels | Build lead deduplication engine | Lead Processing | Lead intake operations | 13 | Sprint 05 | P0 | 2 | FR-LC-007, FR-LC-029
44 | Lead Capture & Lead Management | Lead Intake Operations | Enable all inbound channels | Capture private label brand attribution | Lead Attribution | Lead intake operations | 5 | Sprint 06 | P0 | 0
45 | Lead Capture & Lead Management | Lead Operations | Run the full lead lifecycle | Configure the seven confirmed lead stages | Lead Pipeline | Canonical data model | 8 | Sprint 06 | P0 | 3 | FR-LC-021, FR-LC-024, FR-LC-035
46 | Lead Capture & Lead Management | Lead Operations | Run the full lead lifecycle | Capture the full lead profile | Lead Record | Reference data loaded | 8 | Sprint 06 | P0 | 1 | FR-LC-005
47 | Lead Capture & Lead Management | Lead Routing | Assign leads accurately and quickly | Implement service-tech-count routing | Routing Engine | Lead record and role model | 8 | Sprint 06 | P0 | 2 | FR-LC-013, FR-LC-015
48 | Lead Capture & Lead Management | Lead Operations | Run the full lead lifecycle | Build lead workspace views for list, Kanban, discovery execution, fast-track, and closed-lost handling | Lead Workspace | Lead stages, lead record, and routing rules | 8 | Sprint 06 | P0 | 5 | FR-LC-026, FR-LC-028, FR-LC-030, FR-LC-033, FR-LC-043
49 | CIS, Credit & Onboarding Workflow | CIS Design and Capture | Digitize the CIS experience | Define CIS digital form field specification | CIS Form | Canonical data model | 8 | Sprint 06 | P0 | 10 | FR-CIS-002, FR-CIS-003, FR-CIS-004, FR-CIS-005, FR-CIS-006
50 | CIS, Credit & Onboarding Workflow | CIS Design and Capture | Digitize the CIS experience | Assign distribution center by state at CIS stage | Onboarding | CIS form fields and canonical data | 5 | Sprint 06 | P0 | 2 | FR-CIS-033, FR-CIS-037
51 | CIS, Credit & Onboarding Workflow | Digital CIS | Replace paper onboarding | Build digital CIS forms with signature capture | CIS Experience | Identity patterns | 8 | Sprint 06 | P0 | 3 | FR-CIS-007, FR-CIS-011, FR-CIS-036
52 | CIS, Credit & Onboarding Workflow | Digital CIS | Replace paper onboarding | Separate credit card collection from CIS data | Secure Credit Capture | PCI controls | 8 | Sprint 06 | P0 | 0
53 | Customer, Account, Contact & Multi-Location Management | Contact Management | Implement contact hierarchy and role ordering | Merge bootstrapped contacts into the governed three-contact-role model | Contact Model | Canonical data model | 5 | Sprint 07 | P0 | 7 | FR-CA-017, FR-CA-018, FR-CA-020, FR-CA-022, FR-CA-023
54 | Customer, Account, Contact & Multi-Location Management | Customer 360 | Model the full customer account | Build an Acumatica-aligned customer workspace | Customer Workspace | Canonical data model | 13 | Sprint 07 | P0 | 8 | FR-CA-003, FR-CA-004, FR-CA-009, FR-CA-016, FR-CA-026
55 | Customer, Account, Contact & Multi-Location Management | Customer 360 | Model the full customer account | Capture affinity, ownership, brand, class, and lifecycle context | Customer Workspace | Reference data loaded | 5 | Sprint 07 | P0 | 4 | FR-CA-011, FR-CA-035, FR-CA-039, FR-CA-040
56 | Customer, Account, Contact & Multi-Location Management | Multi-Location Management | Build parent-child location hierarchy and shared account rollups | Bootstrap multi-location hierarchy from Acumatica shipping-address extracts | Multi-Location | Contact model and canonical data | 13 | Sprint 07 | P0 | 4 | FR-CA-027, FR-CA-028, FR-CA-029, FR-CA-033
57 | Dealer Portal Replacement for Shopify | Dealer Identity | Replace Shopify account model | Authenticate dealer users at the customer-account level | Dealer Identity | Customer workspace and access control | 8 | Sprint 07 | P0 | 0
58 | Reports & Analytics | Reporting Foundation | Create trusted reporting data | Build activity categorization taxonomy and enforcement | Activity Taxonomy | Canonical data model | 5 | Sprint 07 | P0 | 0
59 | QA, UAT, Rollout & Adoption | Integration Quality | Validate external contracts before dependent waves scale | Automate contract tests for Acumatica, Outlook, payment, route-provider, and mobile APIs | Contract Testing | Specify APIs, events, schedules, and ownership for customer, order, invoice, payment, shipment, pricing, and product data and Define API versioning, compatibility, and deprecation policy | 8 | Sprint 07 | P0 | 0
60 | QA, UAT, Rollout & Adoption | Release Controls | Reduce blast radius during pilot and launch | Define kill-switch and rollback matrix by module | Operational Controls | Implement feature-flag and cohort-targeting framework | 5 | Sprint 07 | P0 | 0
61 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 03 - Release Buffer | Execute Wave 1 bootstrap migration rehearsal, UAT, bug fixes, deployment, and stabilization | Testing & Release | Seq 03 features complete | 21 | Sprint 08 | P0 | 0
62 | Acumatica Integration & Data Migration | Master Sync | Synchronize account and contact data | Bootstrap customers and contacts from Acumatica, then run governed ongoing sync | Customer Sync | Integration blueprint and customer model | 13 | Sprint 08 | P0 | 0
63 | Acumatica Integration & Data Migration | Product & Pricing Sync | Keep sellable data current | Sync products, variants, price classes, and customer pricing inputs from ERP | Product Sync | Integration blueprint and pricing governance | 13 | Sprint 08 | P0 | 0
64 | Territory Management & Field Routing | Access Views | Tailor territory insight by role | Show TM, RD, VP, and executive scopes with inherited rollups | Role Views | Role-based permissions and org hierarchy | 8 | Sprint 08 | P0 | 1 | FR-TR-043
65 | Territory Management & Field Routing | Routing Integration | Use territory logic in lead assignment | Feed state-based territory ownership into lead routing and customer ownership workflows | Routing Services | Lead routing and territory model | 5 | Sprint 08 | P0 | 2 | FR-TR-006, FR-TR-037
66 | Territory Management & Field Routing | Territory Model | Define and maintain territory ownership | Auto-assign regional director by territory | RD Assignment | Territory model and TM assignment | 5 | Sprint 09 | P0 | 2 | FR-TR-004, FR-TR-005
67 | Communication, Notifications & Alerts | Alert Engine | Create one notification framework | Add credit hold alert delivery to dealer portal users | Dealer Credit Alert | Credit hold sync (INT-006) and dealer identity | 5 | Sprint 09 | P0 | 6 | FR-AN-005, FR-AN-015, FR-AN-017, FR-AN-030, FR-AN-038
68 | Communication, Notifications & Alerts | Lead Alerts | Notify teams about inbound opportunity | Trigger new lead arrival, assignment, and SLA breach notifications | Notification Engine | Lead routing and SLA engine | 5 | Sprint 09 | P0 | 8 | FR-AN-001, FR-AN-002, FR-AN-011, FR-AN-023, FR-AN-029
69 | Lead Capture & Lead Management | Lead Operations | Enforce SLA and routing discipline | Build 48-hour SLA enforcement | Lead SLA | Lead routing and assignment | 8 | Sprint 09 | P0 | 3 | FR-LC-020, FR-LC-036, FR-LC-038
70 | Lead Capture & Lead Management | Lead Operations | Enforce SLA and routing discipline | Build affinity roster bulk import | Lead Import | Canonical data model and reference data | 13 | Sprint 09 | P0 | 4 | FR-LC-006, FR-LC-008, FR-LC-010, FR-LC-019
71 | Lead Capture & Lead Management | Lead Response | Enforce response accountability | Add 48-hour SLA timers and escalation states | SLA Engine | Lead pipeline and alert engine | 8 | Sprint 09 | P0 | 3 | FR-LC-037, FR-LC-039, FR-LC-041
72 | Lead Capture & Lead Management | Lead Routing | Assign leads accurately and quickly | Implement state-based routing | Routing Engine | Territory model | 8 | Sprint 09 | P0 | 1 | FR-LC-014
73 | CIS, Credit & Onboarding Workflow | Credit Workflow | Route credit requests to the right approver | Send Net30 and ACH requests to credit review and verify card-based requests separately | Credit Routing | Secure credit capture | 8 | Sprint 09 | P0 | 0
74 | CIS, Credit & Onboarding Workflow | Onboarding Controls | Standardize post-CIS activation | Build finance approval queue and post-CIS credit routing workflow | Credit Workflow | CIS e-sign and notification engine | 8 | Sprint 10 | P0 | 9 | FR-CIS-016, FR-CIS-018, FR-CIS-019, FR-CIS-020, FR-CIS-021
75 | CIS, Credit & Onboarding Workflow | Onboarding Data Flow | Reuse submitted onboarding data | Auto-populate customer, contact, and billing fields from CIS | Data Mapping | CIS form and customer model | 8 | Sprint 10 | P0 | 1 | FR-CIS-013
76 | CIS, Credit & Onboarding Workflow | Onboarding Control | Standardize post-CIS activation | Build onboarding checklist and readiness gates | Onboarding Checklist | Credit routing and customer model | 8 | Sprint 10 | P0 | 7 | FR-CIS-026, FR-CIS-027, FR-CIS-028, FR-CIS-029, FR-CIS-034
77 | CIS, Credit & Onboarding Workflow | Document Handling | File and retain onboarding artifacts | Migrate active CIS packages into governed document folders and customer context | Document Repository | Digital CIS and asset repository | 5 | Sprint 10 | P1 | 0
78 | Customer, Account, Contact & Multi-Location Management | Activity Management | Preserve field and service interactions | Track visits, calls, trainings, and notes against customer context | Activity Timeline | Customer workspace and mobile activities | 8 | Sprint 10 | P0 | 1 | FR-CA-010
79 | Customer, Account, Contact & Multi-Location Management | Contact Management | Represent customer relationships correctly | Implement contact hierarchy and role ordering | Contact Model | Customer workspace | 8 | Sprint 10 | P0 | 0
80 | Customer, Account, Contact & Multi-Location Management | Customer Activation | Control the ERP activation gate | Propagate Acumatica Customer ID and display sync status | ERP Sync | First-order trigger and Acumatica integration | 5 | Sprint 10 | P0 | 8 | FR-CA-001, FR-CA-013, FR-CA-014, FR-CA-021, FR-CA-031
81 | Customer, Account, Contact & Multi-Location Management | Customer Activation | Control the ERP activation gate | Build BD to TM ownership handoff notification | Ownership Transfer | First-order trigger and territory model | 5 | Sprint 10 | P0 | 2 | FR-CA-002, FR-CA-012
82 | Customer, Account, Contact & Multi-Location Management | Customer Activation | Control the ERP activation gate | Build credit card tokenization workflow | Payment Tokenization | Security review and PCI design | 8 | Sprint 10 | P0 | 1 | FR-CA-045
83 | Customer, Account, Contact & Multi-Location Management | Multi-Location Management | Support enterprise accounts | Build parent-child location hierarchy and shared account rollups | Location Model | Customer workspace | 8 | Sprint 11 | P0 | 0
84 | Customer, Account, Contact & Multi-Location Management | Customer Workspace | Make the account model operable at scale | Build customer list, search, and lifecycle state management | Customer Workspace | Build an Acumatica-aligned customer workspace and lifecycle context | 5 | Sprint 11 | P0 | 4 | FR-CA-005, FR-CA-006, FR-CA-007, FR-CA-008
85 | Dealer Portal Replacement for Shopify | Dealer Catalog | Deliver a B2B product browsing experience | Bootstrap the full catalog with real SKU and variant structure | Product Catalog | Product sync | 13 | Sprint 11 | P0 | 0
86 | Dealer Portal Replacement for Shopify | Dealer Catalog | Deliver a B2B product browsing experience | Provide search, filters, favorites, compare, and quick order | Catalog UX | Product catalog | 8 | Sprint 11 | P0 | 0
87 | Dealer Portal Replacement for Shopify | Dealer Identity | Replace Shopify account model | Build multi-user company access model | Portal Access | Dealer identity and security model | 13 | Sprint 11 | P0 | 0
88 | Dealer Portal Replacement for Shopify | Dealer Ordering | Support complete ordering workflows | Build cart, quick re-order, PO capture, and checkout controls | Checkout | Dealer identity and pricing | 8 | Sprint 11 | P0 | 0
89 | Dealer Portal Replacement for Shopify | Dealer Ordering | Support complete ordering workflows | Handle Canada vs US portal pricing and catalog | Canada/US Handling | Pricing sync and catalog | 8 | Sprint 11 | P0 | 0
90 | Dealer Portal Replacement for Shopify | Dealer Ordering | Persist dealer carts across sessions | Build server-side cart persistence | Checkout | Dealer identity and catalog | 5 | Sprint 12 | P0 | 0
91 | Dealer Portal Replacement for Shopify | Dealer Ordering | Validate orders before checkout submission | Build 6-check checkout validation engine | Checkout | Dealer pricing and credit hold sync | 8 | Sprint 12 | P0 | 0
92 | Dealer Portal Replacement for Shopify | Dealer Pricing | Apply customer-specific commercial rules | Resolve bootstrapped price class, customer class, and discount tier at login and checkout | Dealer Pricing | Pricing config and customer identity | 8 | Sprint 12 | P0 | 0
93 | Dealer Portal Replacement for Shopify | Dealer Visibility | Give companies shared operational visibility | Enable invoice PDF download | Invoice Download | ERP financial visibility sync (INT-005) | 5 | Sprint 12 | P0 | 0
94 | Dealer Portal Replacement for Shopify | Dealer Identity | Provision dealer company access from onboarding | Bootstrap dealer company admin, users, and enrollment workflow from approved onboarding and Shopify exports | Portal Provisioning | Onboarding approval, dealer identity, customer model, and pricing context | 8 | Sprint 12 | P0 | 0
95 | Dealer Portal Replacement for Shopify | Commerce Readiness Gates | Prove catalog and pricing foundations before dealer rollout | Certify product sync, pricing sync, dealer-group resolution, and publish validation before portal catalog and checkout rollout | Portal Readiness Gate | Sync products, variants, price classes, and customer pricing inputs from ERP and Build 12-point publish validation rule engine | 5 | Sprint 12 | P0 | 0
96 | Product Management & Dealer Catalog Governance | Dealer Group Model | Define account-driven catalog groups | Resolve dealer groups from migrated account setup | Dealer Group Resolver | Reference data loaded and customer account model | 8 | Sprint 12 | P0 | 0
97 | Product Management & Dealer Catalog Governance | Group-First Workflow | Make Product Management back-office and group-first | Build dealer-group-first workflow | Product Management Workspace | Dealer group resolver and product sync | 8 | Sprint 12 | P0 | 0
98 | Product Management & Dealer Catalog Governance | Product Sync | Handle Acumatica sync conflicts safely | Implement sync conflict resolution algorithm | Product Sync | Integration blueprint and product master sync | 8 | Sprint 12 | P0 | 0
99 | Pricing & ERP-Dependent Commercial Rules | Pricing Governance | Govern commercial pricing inputs | Handle Canada price list separation in CRM and portal | Canada Pricing | Acumatica pricing sync (INT-003) and Canada portal handling | 8 | Sprint 13 | P0 | 3 | FR-PR-027, FR-PR-030, FR-PR-035
100 | Training Management | Completion Tracking | Prove what was delivered | Backfill structured training history, completion evidence, and follow-up tasks from legacy sources | Training Records | Training calendar | 8 | Sprint 13 | P0 | 5 | FR-TM-022, FR-TM-023, FR-TM-028, FR-TM-036, FR-TM-043
101 | Training Management | Training Record Operations | Track activity and proof at the customer level | Capture training type on every training record | Training Records | Training module | 3 | Sprint 13 | P0 | 6 | FR-TM-001, FR-TM-005, FR-TM-025, FR-TM-026, FR-TM-046
102 | Training Management | Training Record Operations | Track activity and proof at the customer level | Enforce site visit versus training distinction | Activity Model | Activity categorization taxonomy | 5 | Sprint 13 | P0 | 2 | FR-TM-041, FR-TM-045
103 | Training Management | Training Scheduling | Manage training commitments from CRM | Schedule training against customers, users, and calendars | Training Calendar | Customer model and calendar foundation | 8 | Sprint 13 | P0 | 2 | FR-TM-015, FR-TM-048
104 | Consignment Management | Audit Cycle | Enforce the 90-day operating rhythm | Build TM consignment dashboard (web) | TM Dashboard | Site master and audit cycle | 8 | Sprint 13 | P0 | 2 | FR-CSG-009, FR-CSG-051
105 | Consignment Management | Consignment Enrollment | Launch and manage the program correctly | Flag accounts as consignment customers and capture digital agreements | Consignment Enrollment | Customer model and document repository | 8 | Sprint 13 | P0 | 4 | FR-CSG-001, FR-CSG-002, FR-CSG-003, FR-CSG-004
106 | Consignment Management | Consignment Onboarding | Standardize new consignment setup | Build the six-step onboarding wizard from the checklist | Consignment Wizard | Enrollment baseline | 8 | Sprint 13 | P0 | 7 | FR-CSG-014, FR-CSG-015, FR-CSG-016, FR-CSG-017, FR-CSG-018
107 | Consignment Management | Initial Verification | Establish starting inventory truth | Digitize the initial inventory verification form | Inventory Verification | Consignment wizard | 8 | Sprint 13 | P0 | 2 | FR-CSG-006, FR-CSG-047
108 | Consignment Management | Location Master | Bring real consignment locations into CRM | Load active, new, and exited consignment sites with warehouse identifiers and in-scope documents | Consignment Master | Data migration and customer locations | 8 | Sprint 14 | P0 | 1 | FR-CSG-043
109 | Consignment Management | Site Setup | Onboard new consignment locations correctly | Enforce warehouse naming convention on site creation | Site Admin | Acumatica consignment sync | 5 | Sprint 14 | P0 | 4 | FR-CSG-005, FR-CSG-027, FR-CSG-035, FR-CSG-044
110 | Consignment Management | Site Setup | Enforce consistent warehouse naming | Validate warehouse naming convention on site creation | Site Admin | Acumatica consignment sync | 3 | Sprint 14 | P0 | 0
111 | Consignment Management | Audit Cycle | Enforce the 90-day operating rhythm | Schedule audits, track due dates, and surface 60-day and 90-day status | Audit Scheduler | Consignment master and alert engine | 13 | Sprint 14 | P0 | 5 | FR-CSG-011, FR-CSG-012, FR-CSG-013, FR-CSG-024, FR-CSG-025
112 | Consignment Management | Reconciliation Workflow | Replace Excel and Dropbox reconciliation | Build expected-versus-counted reconciliation with variance handling | Reconciliation | Audit scheduler and inventory baseline | 13 | Sprint 14 | P0 | 1 | FR-CSG-026
113 | Consignment Management | Operational Readiness Gates | Prove consignment foundations before downstream automation | Certify site master, audit scheduler, and reconciliation readiness before PO clock, dashboards, and mobile audit scale-out | Consignment Readiness Gate | Schedule audits, track due dates, and surface 60-day and 90-day status and Build expected-versus-counted reconciliation with variance handling | 5 | Sprint 14 | P0 | 7 | FR-CSG-010, FR-CSG-021, FR-CSG-041, FR-CSG-045, FR-CSG-046
114 | Mobile Field App | Customer Access | Make customer data usable on the road | Provide mobile search, account detail, contacts, and recent activity | Mobile Customer Workspace | Customer model | 8 | Sprint 14 | P0 | 0
115 | Mobile Field App | Field Dashboard | Give reps a task-first mobile home | Show assigned visits, overdue leads, routes, and alerts on the landing screen | Mobile Dashboard | Lead, customer, and alert feeds | 8 | Sprint 14 | P0 | 0
116 | Mobile Field App | Route Execution | Replace Map My Customer core workflows | Support route planning, optimization, and navigation handoff | Route Planner | Territory map and geo services | 13 | Sprint 15 | P0 | 0
117 | Mobile Field App | Visit Capture | Record work at the point of service | Provide GPS check-in and check-out with visit notes | Visit Logging | Mobile customer workspace | 8 | Sprint 15 | P0 | 0
118 | Reports & Analytics | Priority Reports | Deliver the five approved report families | Build site visit report | Site Visit Report | Activity taxonomy and reporting semantic layer | 5 | Sprint 15 | P0 | 0
119 | Reports & Analytics | Reporting Foundation | Create trusted reporting data | Build a reporting semantic layer spanning CRM, dealer, training, consignment, and ERP facts | Reporting Model | Canonical data model and integration blueprint | 13 | Sprint 15 | P0 | 0
120 | Reports & Analytics | Reporting Governance | Make dashboard metrics trustworthy | Publish a metric definition register | Metric Governance | Reporting semantic layer and data stewardship | 8 | Sprint 15 | P0 | 0
121 | Reports & Analytics | Reporting Workspace | Provide role-based dashboard entry points | Build reporting home and role routing | Reporting Workspace | Access control and reporting semantic layer | 8 | Sprint 15 | P0 | 0
122 | QA, UAT, Rollout & Adoption | Quality Strategy | Test the system as a business program | Define end-to-end test coverage for workflows, integrations, data, mobile, and security | QA Plan | Governance cadence and integration blueprint | 8 | Sprint 15 | P0 | 0
123 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 04 - Release Buffer | Execute Wave 2 migration rehearsal, UAT, bug fixes, deployment, and stabilization | Testing & Release | Seq 04 features complete | 55 | Sprint 16 | P0 | 0
124 | Mobile Field App | Lead Workflow | Make assigned leads actionable from the field | Build mobile lead inbox and lead detail workflow | Mobile Lead Workspace | Lead routing, notification engine, and mobile foundation | 8 | Sprint 16 | P0 | 0
125 | Mobile Field App | Mobile Foundation | Build a reliable and adoptable mobile platform | Build push notification receipt and user preferences | Push Notifications | Notification engine (INT-020) and mobile API | 8 | Sprint 17 | P0 | 0
126 | Mobile Field App | Consignment Operations | Support consignment workflows from the field | Build mobile consignment audit flow | Mobile Audit | Consignment module and Acumatica sync | 13 | Sprint 17 | P0 | 0
127 | Mobile Field App | Consignment Operations | Support consignment workflows from the field | Build mobile consignment site dashboard | Mobile Dashboard | Consignment site master and mobile offline | 5 | Sprint 17 | P0 | 0
128 | Mobile Field App | Consignment Operations | Support consignment workflows from the field | Build mobile signature capture | Signature | Mobile audit flow and document model | 5 | Sprint 17 | P0 | 0
129 | Mobile Field App | Consignment Operations | Support consignment workflows from the field | Build mobile photo upload for consignment audit | Photo Upload | Mobile audit flow and document model | 5 | Sprint 17 | P0 | 0
130 | Mobile Field App | Field Navigation | Preserve Map My Customer replacement behaviors | Build mobile deep-link and context routing from alerts, leads, map, and consignment tasks | Mobile Context Routing | Notification engine, route planner, and mobile navigation shell | 5 | Sprint 17 | P0 | 0
131 | Mobile Field App | Field Scheduling | Keep the field team organised and on-time | Build training scheduling from mobile | Mobile Scheduling | Training module and Outlook calendar sync (INT-009) | 8 | Sprint 17 | P0 | 0
132 | Mobile Field App | Visit Capture | Enforce visit workflow with geofencing | Build 100m geofencing with mandatory check-out workflow | Visit Logging | Mobile customer workspace and GPS services | 5 | Sprint 17 | P0 | 0
133 | QA, UAT, Rollout & Adoption | Release & Stabilization | M-Seq 03 - Release Buffer | UAT, bug fixes, deployment, stabilization | Testing & Release | M-Seq 03 features complete | 8 | Sprint 17 | P0 | 0
134 | Acumatica Integration & Data Migration | Legacy CRM Migration | Preserve operational history | Migrate lead, account, contact, activity, and lead-source attribution data from Dynamics CRM and related spreadsheets | Migration | Canonical data model | 13 | Sprint 18 | P0 | 0
135 | Acumatica Integration & Data Migration | Transaction Sync | Expose order and finance history | Bootstrap recent orders, invoices, shipments, statements, and payment status into CRM and dealer views | Transaction Sync | Integration blueprint and dealer account center | 13 | Sprint 18 | P0 | 0
136 | Communication, Notifications & Alerts | Credit & Collections Alerts | Make financial blockers visible | Notify on credit approvals, credit holds, invoice aging, and past-due status | Notification Engine | Financial sync and dealer account center | 8 | Sprint 18 | P0 | 2 | FR-AN-022, FR-AN-026
137 | Lead Capture & Lead Management | Lead Conversion | Turn qualified prospects into customers | Trigger customer creation on first order with onboarding handoff | Conversion Workflow | Customer model and integration blueprint | 8 | Sprint 18 | P0 | 2 | FR-LC-031, FR-LC-032
138 | Dealer Portal Replacement for Shopify | Dealer Credit & Collections | Reflect financial constraints | Block ordering for credit-hold accounts and surface aging alerts | Dealer Account Center | Financial sync and alert engine | 8 | Sprint 18 | P0 | 0
139 | Dealer Portal Replacement for Shopify | Dealer Visibility | Give companies shared operational visibility | Show company-wide orders, invoices, statements, shipments, and payments | Dealer Account Center | Dealer identity and transaction sync | 13 | Sprint 18 | P0 | 0
140 | Dealer Portal Replacement for Shopify | Dealer Visibility | Give dealers self-service access to invoices | Enable invoice PDF download from dealer portal | Dealer Account Center | ERP financial visibility sync (INT-005) | 5 | Sprint 18 | P0 | 0
141 | Dealer Portal Replacement for Shopify | Checkout Governance | Keep portal ordering aligned with finance and account policy | Enforce billing-address governance and launch payment-scope policy | Checkout Governance | Authenticate dealer users at the customer-account level and Build credit card tokenization workflow | 5 | Sprint 19 | P0 | 0
142 | Product Management & Dealer Catalog Governance | Account Context | Use the same dealer context across portal and product management | Resolve dealer group from live account setup | Dealer Context Service | Dealer identity and customer account model | 8 | Sprint 19 | P0 | 0
143 | Product Management & Dealer Catalog Governance | File Governance | Attach the right branded files to each dealer group | Link migrated images, brochures, spec sheets, and install guides | Product File Linking | Asset repository and dealer group resolver | 8 | Sprint 19 | P0 | 0
144 | Product Management & Dealer Catalog Governance | Go-Live Control | Make dealer catalog releases safe | Run dealer-group go-live checks | Go-Live Checklist | Group-first workflow and product file linking | 5 | Sprint 19 | P0 | 0
145 | Product Management & Dealer Catalog Governance | Go-Live Control | Prevent incomplete products from reaching dealers | Build 12-point publish validation rule engine | Go-Live Checklist | Product workspace and file linking | 5 | Sprint 19 | P0 | 0
146 | Pricing & ERP-Dependent Commercial Rules | Checkout Resolution | Handle pricing exceptions safely at the point of order | Build price-not-found, stale-price, and conflicting-price-class resolution workflow | Pricing Exception Handling | Resolve price class, customer class, and discount tier at login and checkout | 5 | Sprint 19 | P0 | 15 | FR-PR-001, FR-PR-002, FR-PR-004, FR-PR-006, FR-PR-009
147 | Pricing & ERP-Dependent Commercial Rules | Pricing Governance | Preserve price history and override accountability | Build effective-dated price history, override audit, and publish accountability | Pricing History | Manage price books, tiers, and account pricing rules in a controlled admin workflow and Sync approved price changes to dealer experiences on a controlled schedule | 8 | Sprint 19 | P0 | 4 | FR-PR-005, FR-PR-014, FR-PR-018, FR-PR-020
148 | Digital Assets & Document Handling | Asset Serving | Make product and dealer assets usable without Widen or Dropbox hunts | Serve curated Widen and Dropbox assets through stable dealer-group-aware links | Asset Delivery Service | Asset repository and dealer group resolver | 8 | Sprint 19 | P0 | 12 | FR-DA-005, FR-DA-007, FR-DA-016, FR-DA-017, FR-DA-018
149 | Digital Assets & Document Handling | Asset Workflow | Govern file uploads and approvals | Build upload, version, and approval workflow for product and dealer files | Asset Workflow | Asset repository and access control | 8 | Sprint 19 | P0 | 8 | FR-DA-001, FR-DA-003, FR-DA-011, FR-DA-012, FR-DA-013
150 | Training Management | Training Proof | Turn training into executive proof | Surface yearly hours delivered, customer summaries, and proof-letter generation | Training Analytics | Training records and report templates | 8 | Sprint 19 | P0 | 1 | FR-TM-002
151 | Training Management | Training Proof | Turn training into executive proof | Build training proof letter generation | Proof Engine | Training records and reporting model | 8 | Sprint 20 | P0 | 4 | FR-TM-009, FR-TM-010, FR-TM-011, FR-TM-037
152 | Consignment Management | Audit Cycle | Enforce the 90-day operating rhythm | Build 5-day PO clock timer | PO Recovery | Reconciliation workflow and notification engine | 8 | Sprint 20 | P0 | 1 | FR-CSG-042
153 | Mobile Field App | Offline Reliability | Keep the app usable without connectivity | Cache assignments, records, and assets with sync queues | Offline Sync | Mobile foundation and API contract | 13 | Sprint 20 | P0 | 0
154 | Reports & Analytics | Priority Reports | Deliver the five approved report families | Build warranty and support report | Warranty Report | Activity taxonomy and reporting semantic layer | 8 | Sprint 20 | P0 | 0
155 | Reports & Analytics | Report Builder | Make reporting self-serve | Build a dynamic report builder with field picker, filters, date logic, and saved views | Report Builder | Reporting semantic layer | 13 | Sprint 20 | P0 | 0
156 | Reports & Analytics | Report Builder | Enable flexible self-service analysis | Build arbitrary parameter report UI | Parameter UI | Reporting semantic layer | 13 | Sprint 20 | P0 | 0
157 | Reports & Analytics | Role Dashboards | Support finance and operations readiness decisions | Build Finance & Ops readiness dashboard | Finance & Ops Readiness | Metric governance and onboarding workflow | 8 | Sprint 21 | P0 | 0
158 | Reports & Analytics | Role Dashboards | Give TMs a daily operating dashboard | Build TM territory dashboard | TM Territory Dashboard | Metric governance, territory model, and activity taxonomy | 5 | Sprint 21 | P0 | 0
159 | Reports & Analytics | Role Dashboards | Give RDs a subordinate rollup view | Build RD rollup dashboard | RD Rollup Dashboard | Metric governance and TM territory metrics | 5 | Sprint 21 | P0 | 0
160 | Reports & Analytics | Template Reports | Deliver the executive approval-gate reports | Build TM Sales YoY and territory sales views | Template Reports | Reporting model | 8 | Sprint 21 | P0 | 0
161 | Reports & Analytics | Template Reports | Deliver the executive approval-gate reports | Build affinity group sales and market penetration reports | Template Reports | Reporting model and affinity master data | 8 | Sprint 21 | P0 | 0
162 | Reports & Analytics | Template Reports | Deliver the executive approval-gate reports | Build leads-to-revenue and lead performance reports | Template Reports | Lead model and order linkage | 8 | Sprint 21 | P0 | 0
163 | Reports & Analytics | Template Reports | Deliver the executive approval-gate reports | Build training-hours reports by customer, TM, and type | Template Reports | Training records | 8 | Sprint 21 | P0 | 0
164 | Reports & Analytics | Template Reports | Deliver the executive approval-gate reports | Build product mix and revenue composition reports | Template Reports | Product and order facts | 8 | Sprint 21 | P0 | 0
165 | Reports & Analytics | KPI Governance | Keep dashboards and exported reports consistent | Load KPI baseline packs and build lineage/reconciliation testing across dashboards, builder outputs, and exports | KPI Reconciliation | Build a reporting semantic layer spanning CRM, dealer, training, consignment, and ERP facts and Publish a metric definition register | 8 | Sprint 21 | P0 | 0
166 | Executive Dashboard | Consignment Pulse | Give leadership a live consignment readout | Show active sites, audit status, value at risk, and overdue actions | Consignment Widgets | Consignment dashboard | 5 | Sprint 22 | P0 | 0
167 | Executive Dashboard | Executive KPI Framework | Give leadership one trusted command center | Compose the executive dashboard from governed report components | Executive Dashboard | Reporting semantic layer | 8 | Sprint 22 | P0 | 0
168 | Executive Dashboard | Funnel Health | Expose pipeline quality | Surface lead funnel status, aging, and conversion signals | Pipeline Widgets | Lead reporting and SLA engine | 5 | Sprint 22 | P0 | 0
169 | Executive Dashboard | Revenue Monitoring | Track top-line movement clearly | Show this month, last month, and same month last year revenue | Revenue Cards | Executive KPI framework | 5 | Sprint 22 | P0 | 0
170 | Executive Dashboard | Training Proof | Put training value in front of executives | Show YTD training hours, prior-year comparison, and summary access | Training Widgets | Training reports | 5 | Sprint 22 | P0 | 0
171 | QA, UAT, Rollout & Adoption | Business Rule Testing | Validate the rules that matter most | Create test packs for service-tech routing, SLA timers, credit workflow, company-order visibility, and consignment audit cycle | QA Packs | Quality strategy | 8 | Sprint 22 | P0 | 0
172 | QA, UAT, Rollout & Adoption | Role-Based UAT | Get the right users validating the right flows | Run UAT for admins, TMs, RDs, VPs, CSRs, and dealer contacts | UAT | Quality strategy and role matrix | 8 | Sprint 22 | P0 | 0
173 | QA, UAT, Rollout & Adoption | Pilot Governance | Control pilot-to-GA progression | Define pilot cohorts, success metrics, and GA go-no-go gate | Pilot Governance | UAT, reconciliation, role training, and support model | 8 | Sprint 22 | P0 | 0
174 | QA, UAT, Rollout & Adoption | Operational Resilience | Prove recovery paths before broad rollout | Run resilience and failover drills across queues, auth, storage, reporting jobs, and alert delivery | Resilience Drills | Show sync status, errors, retries, dead-letter items, and exception queues and Define kill-switch and rollback matrix by module | 8 | Sprint 22 | P0 | 0
175 | QA, UAT, Rollout & Adoption | Operational Resilience | Tie production support to explicit thresholds | Define service thresholds and Sev-based operational response | Operational SLA Model | Stand up issue triage, daily review, and resolution ownership for early launch weeks | 5 | Sprint 22 | P0 | 0
176 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 05 - Release Buffer | Complete integrated UAT, defect triage, and release-candidate sign-off | Testing & Release | Seq 05 features complete | 34 | Sprint 23 | P0 | 0
177 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 05 - Release Buffer | Execute final migration rehearsal, cutover readiness, smoke validation, and rollback checks | Testing & Release | Complete integrated UAT, defect triage, and release-candidate sign-off | 34 | Sprint 23 | P0 | 0
178 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 05 - Release Buffer | Run post-launch stabilization window and confirm go-live exit criteria | Testing & Release | Execute deployment rehearsal, cutover readiness, smoke validation, and rollback checks | 21 | Sprint 24 | P0 | 0
179 | QA, UAT, Rollout & Adoption | Hypercare | Support the first live operating period | Stand up issue triage, daily review, and resolution ownership for early launch weeks | Hypercare | Pilot gate and cutover plan | 8 | Sprint 24 | P0 | 0
180 | QA, UAT, Rollout & Adoption | Training & SOPs | Prepare the organization to adopt the platform | Deliver role-based training, SOPs, and admin runbooks | Enablement | UAT feedback, approved workflows, and pilot cohort | 8 | Sprint 24 | P0 | 0
181 | Mobile Field App | Offline Reliability | Keep the app usable without connectivity | Build offline data conflict review on reconnect | Conflict Resolution | Mobile offline sync | 8 | Sprint 24 | P0 | 0
182 | Mobile Field App | Offline Reliability | Prioritize offline sync by data importance | Build offline sync queue with priority levels | Offline Sync | Mobile foundation and offline framework | 5 | Sprint 24 | P0 | 0
183 | QA, UAT, Rollout & Adoption | Release & Stabilization | M-Seq 04 - Release Buffer | UAT, bug fixes, deployment, stabilization | Testing & Release | M-Seq 04 features complete | 5 | Sprint 24 | P0 | 0
184 | Mobile Field App | Go-Live Readiness | Prepare the mobile app for production deployment | Submit to iOS App Store and Google Play Store | App Distribution | Mobile UAT sign-off | 13 | Sprint 24 | P0 | 0
185 | QA, UAT, Rollout & Adoption | Release & Stabilization | M-Seq 05 - Release Buffer | UAT, bug fixes, deployment, stabilization | Testing & Release | M-Seq 05 features complete | 5 | Sprint 25 | P0 | 0
186 | Acumatica Integration & Data Migration | Cutover Reconciliation | Prove the new platform is trustworthy | Run final migration dry-runs, compare totals, and reconcile sample records before launch | Reconciliation | All migration streams | 8 | Sprint 25 | P0 | 0
187 | Acumatica Integration & Data Migration | Migration Operations | Capture data changes between rehearsal and cutover | Build migration delta capture queries per source system | Migration | All migration streams and cutover plan | 8 | Sprint 25 | P0 | 0
188 | Acumatica Integration & Data Migration | Migration Operations | Enable safe migration rollback | Build rollback procedures and scripts per migration wave | Migration | All migration streams | 5 | Sprint 25 | P0 | 0
189 | QA, UAT, Rollout & Adoption | Cutover Planning | Launch with control | Plan deployment, freeze windows, communications, and rollback options | Cutover Plan | Reconciliation and readiness tests | 8 | Sprint 25 | P0 | 0
190 | QA, UAT, Rollout & Adoption | Cutover Governance | Control go-live execution minute by minute | Build cutover command-center runbook with validation checkpoints and rollback triggers | Cutover Runbook | Plan deployment, freeze windows, communications, and rollback options and Define service thresholds and Sev-based operational response | 5 | Sprint 25 | P0 | 0
191 | QA, UAT, Rollout & Adoption | Release & Stabilization | Seq 06 - Release Buffer | UAT, bug fixes, deployment, stabilization | Testing & Release | Seq 06 features complete | 21 | Sprint 25 | P0 | 0