## Monthly Plan
Dynamic AQS CRM — Monthly Release Plan
Month | Covered Sprints | Release | Monthly Goal | Included Scope | Third-Party / Integration Focus | Gate / Exit Signal
Jun 2026 | Sprint 01-02 | Release 1 | Establish the program foundation and secure delivery baseline | Governance, architecture boundaries, environments, CI/CD, role security, PCI controls | None beyond foundation setup; program prepares Acumatica and Microsoft dependencies | Foundation approved and secure build path proven
Jul 2026 | Sprint 03-04 | Release 1 | Lock integration contracts and platform controls before scaling build | Third-party integration inventory, field mappings, Acumatica contract definition, sandbox readiness, migration tolerances, mobile foundation | Acumatica contract inventory, third-party integration tracker, sandbox certification | Release 1 can scale only if contracts, mappings, and sandbox evidence are trusted
Aug 2026 | Sprint 05-06 | Release 1 | Stand up the intake and onboarding backbone | Alert engine, SMTP/M365 dispatch, branded lead forms, routing, digital CIS, secure tokenized payment entry | SMTP / Microsoft 365 dispatch and tokenized payment capture become active design items | Internal alpha closes only after lead-to-CIS flow is trusted
Sep 2026 | Sprint 07-09 | Release 2 | Prove the customer/account and early portal foundation | Customer workspace, dealer auth, contract tests, Acumatica bootstrap sync, product and pricing sync, credit alerts | Acumatica bootstrap feeds, dealer auth, early notification consumption | Closed pilot stays limited until customer and portal trust improves
Oct 2026 | Sprint 10-11 | Release 2 | Control activation, dealer enrollment, and catalog readiness | Payment token callback handling, customer activation gate, full dealer catalog bootstrap, cart and checkout controls | Regional payment gateway handoff, Shopify enrichment inputs, invoice documents | Dealer pilot cannot widen until catalog, checkout, and activation are governed
Nov 2026 | Sprint 12-13 | Release 2 -> Release 3 | Finish pilot portal controls and open the training foundation | Portal validation, dealer user migration, invoice access, training history backfill, customer-centric training scheduling | Shopify migration inputs, Outlook-linked training model, legacy training history sources | Shift into Release 3 only after dealer pilot controls and training foundations are stable
Dec 2026 | Sprint 14-15 | Release 3 | Build field and consignment operational visibility | Consignment reconciliation foundation, mobile search and landing views, routing, check-in/out, site visit and support reporting | Dropbox consignment documents and map provider dependencies are now operationally important | Field teams need trustworthy route, visit, and consignment context before wider rollout
Jan 2027 | Sprint 16-17 | Release 3 | Make mobile execution real for training and consignment | Mobile lead inbox, push notifications, consignment audits, signatures, photos, Outlook-linked scheduling, confirmation emails | Outlook calendar, email confirmations, and mobile push providers are now on the critical path | Release 3 trust depends on mobile execution outperforming the current fragmented field stack
Feb 2027 | Sprint 18-19 | Release 3 | Open financial visibility and asset delivery for representative accounts | Transaction sync, dealer financial visibility, payment gateway routing, Widen/Dropbox migration, S3 + CloudFront asset delivery, proof-letter support | Acumatica transaction feeds, regional payment gateways, Widen, Dropbox, S3, and CloudFront are all active concerns | Limited availability exits only if finance visibility and digital asset delivery work cleanly
Mar 2027 | Sprint 20-22 | Release 3 -> Release 4 | Close pilot reporting and start GA-hardening | Report builder, proof letters, KPI baselines, semantic-layer trust, dashboards, resilience drills, service thresholds | Reporting delivery channel, storage monitoring, and platform operations hardening come to the front | GA prep begins only once reporting and service thresholds are credible
Apr 2027 | Sprint 23-24 | Release 4 | Harden supportability, offline behaviour, and rollout readiness | UAT, support runbooks, pilot exit evidence, offline sync hardening, app-store submission, final go-live checks | App stores, support operations, and integration replay controls must be ready for production widening | Launch readiness depends on supportability and offline/mobile stability
May 2027 | Sprint 25 | Release 4 | Execute cutover and controlled launch | Migration dry-runs, delta capture, rollback scripts, cutover command center, launch buffer and stabilization | Legacy-source delta capture, final communication channels, and rollback tooling are all active | Controlled GA only after cutover validation and rollback proof are complete

## Release Goals
Release Goals And Included Scope
Release | Window | Sprints | Planned SP | Release Goal | What It Includes | Third-Party Focus | Exit Gate
Release 1 | Jun 02, 2026 - Aug 24, 2026 | Sprint 01-06 | 391 | Build the secure platform and onboarding foundation | Program governance, architecture boundaries, environments, CI/CD, security, alert engine, lead intake, CIS, tokenized payment entry | Acumatica contract design, third-party inventory, SMTP/M365 dispatch, tokenized payment capture | Move to Release 2 only after internal alpha proves the core flow can be executed safely
Release 2 | Aug 25, 2026 - Nov 16, 2026 | Sprint 07-12 | 371 | Prove customer activation and dealer pilot controls | Account workspace, dealer auth, product and pricing bootstrap, portal ordering controls, dealer migration, training foundations | Acumatica bootstrap sync, Shopify migration inputs, payment gateway handoff, invoice document links | Move to Release 3 only after internal/dealer pilot trust is achieved
Release 3 | Nov 17, 2026 - Mar 08, 2027 | Sprint 13-20 | 514 | Deliver field execution, financial visibility, and bounded digital-asset replacement | Training history, consignment workflow, mobile execution, dealer finance visibility, Widen/Dropbox migration, S3/CloudFront delivery, report builder | Outlook calendar and email, mobile push, Acumatica transactions, payment gateway routing, Widen/Dropbox, S3, CloudFront | Move to Release 4 only after pilot exit metrics and asset/finance workflows are stable
Release 4 | Mar 09, 2027 - May 17, 2027 | Sprint 21-25 | 327 | Harden reporting, supportability, cutover, and launch controls | Semantic layer, KPI baselines, dashboards, resilience, offline hardening, support runbooks, app stores, cutover, rollback, launch buffer | Reporting delivery, source-system delta capture, support command center, rollback tooling | Widen by wave only after cutover proof and launch controls are green

## Monthly Milestones
Monthly Milestones And Gates
Month | Milestone | Planned Date | Owner | Depends On
Jun 2026 | Foundation baseline approved | 2026-06-15 | Program Manager | Governance + architecture signed
Jul 2026 | Acumatica contract and third-party inventory baseline signed | 2026-07-27 | Architecture Lead | Integration contract and sandbox path trusted
Aug 2026 | Release 1 internal alpha exit | 2026-08-24 | Product + Engineering | Lead-to-CIS foundation trusted
Sep 2026 | Customer/account bootstrap complete | 2026-09-21 | Ops Lead | Pilot account sync and auth stable
Oct 2026 | Portal catalog and checkout gate | 2026-10-19 | Portal Lead | Catalog, checkout, and payment handoff proven
Nov 2026 | Release 2 pilot exit | 2026-11-16 | Ops Lead | Dealer pilot controls trusted
Dec 2026 | Consignment and field visibility baseline ready | 2026-12-28 | Field Operations Lead | Field and consignment views trusted
Jan 2027 | Mobile execution + Outlook sync live in pilot | 2027-01-25 | Mobile Lead | Scheduling and mobile audit flows trusted
Feb 2027 | Financial visibility and asset delivery gate | 2027-02-22 | Portal + Asset Leads | Transactions, payment routing, and asset delivery stable
Mar 2027 | Release 3 exit / Release 4 start | 2027-03-08 | Program Manager | Pilot exit evidence accepted
Apr 2027 | Support and offline hardening complete | 2027-04-30 | Support Lead | UAT, offline, and support runbooks green
May 2027 | GA cutover gate | 2027-05-17 | Executive Steering Board | Delta, rollback, and launch controls proven

## Rollout & Gates
Rollout Waves And Release Gating
Release | Wave | Audience | What Opens | Fallback / Guardrail
Release 1 | Wave 0 / Internal Alpha | Internal users in non-prod | Secure foundation, mappings, and core workflow proof | No dealer exposure; no production ordering
Release 2 | Wave 1 / Closed Pilot | Representative internal + dealer pilot cohort | Customer activation, dealer auth, and portal controls trusted | Keep cohort small if account/portal trust slips
Release 3 | Wave 2 / Limited Availability | Selected dealer groups and field teams | Mobile, consignment, finance visibility, and digital assets stable | Fallback to pilot cohort if finance or asset workflows degrade
Release 4 | Wave 3 / Controlled GA | Phased by region, dealer group, and function | Reporting, support, cutover, and rollback proof complete | Pause widening by group/region if launch metrics degrade